| ADANSI SOUTH DISTRICT ASSEMBLY |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2021 ANNUAL ACTION PLAN FOR THE IMPLEMENTATION OF 2018-2021 DMTDP |  |  |  |  |  |  |  |  |  |  |  |  |
| S/N | Activity | Location | Output Indicators | Quarterly schedule |  |  |  | Indicative Budget |  |  |  |  |
|  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Donor | Lead | Collab. |
| 1 | Re-valuation of property | District Wide | Number of properties valued |  |  |  |  | 10,000.00 |  |  | CA | DA |
| 2 | Prepare District Composite Budget | DA | District Composite Budget prepared |  |  |  |  | 15,000.00 |  |  | CA | DA |
| 3 | Create a data base on revenue items | District Wide | Data base on revenue items created |  |  |  |  |  | 5,000.00 |  | CA | DA |
| 4 | Procure value books and other logistics for revenue collection | DA | No. of value books and logistics procured |  |  |  |  |  | 5,000.00 |  | CA | DA |
| 6 | Establishment of revenue collection points | District Wide | No. of revenue check points established |  |  |  |  | 30,000.00 |  |  | Works | DA |
| 7 | Supply and installation of accounting software | DA | No. of soft wares supplied and installed |  |  |  |  | 15,000.00 |  |  | CA | DA |
| 8 | Training of revenue collection and account staff | DA | No. of revenue collectors/ accounts staff trained |  |  |  |  | 15,000.00 |  | 15,000.00 | CA | DA |
| 9 | Construct market stalls/ stores | Atobiase, | No. of market stalls constructed |  |  |  |  | 150,000.00 | 50,000.00 |  | Works | DA |
| 10 | Generate and produce market information | District Wide | Amount of market information generated |  |  |  |  | 5,000.00 |  |  | CA | DA |
| 11 | Organize training for farmers in accessing financial support | District Wide | No. of farmers trained |  |  |  |  | 7,000.00 |  |  | Agric | DA |
| 12 | Facilitate the supply of farm inputs and credit facilities | District Wide | No. of farmers supplied with farm inputs and credit facilities |  |  |  |  | 5,000.00 |  |  | Agric | DA |
| 13 | Facilitate cocoa spraying programme | District Wide | No. of farms sprayed |  |  |  |  | 10,000.00 |  |  | Agric | DA |
| 14 | Provide extension services of crops and livestock | District Wide | No. of farmers with access to extension services for crops/ livestock |  |  |  |  | 6,000.00 |  |  | Agric | DA |
| 15 | Conduct disease surveillance | District Wide | No. of surveillance conducted |  |  |  |  |  | 5,000.00 |  | Agric | DA |
| 16 | Organize training for AEAs | District Wide | No. of AEAs trained |  |  |  |  |  | 5,000.00 |  | Agric | DA |
| 17 | Provide extension delivery | District Wide | No. of farmers with access to extension service |  |  |  |  |  | 5,000.00 |  | Agric | DA |
| 18 | Provide vaccination for livestock |  | No. of vaccinations done |  |  |  |  |  | 2,000.00 |  |  | DA |
| 19 | Support District Rice Extension Plan and other donor programs and projects | District Wide | No. of activities supported |  |  |  |  | 20,000.00 |  |  | Agric | DA |
| 20 | Support the Modernizing Agriculture in Ghana Program |  | Amount of funds disbursed on program |  |  |  |  |  |  | 1000,000.00 | Agric | DA |
| 21 | Establishment of 48 demonstrations and field days | District Wide | No. of demonstrations and field days organized |  |  |  |  | 10,000.00 |  |  | Agric | DA |
| 22 | Protect forest reserves and water bodies | District Wide | Coverage of forest reserves and water bodies |  |  |  |  | 10,000.00 |  |  | FSD | DA |
| 23 | Embark on tree planting | District Wide | No. of trees planted |  |  |  |  | 10,000.00 |  |  | FSD | DA |
| 24 | Monitor activities of illegal lumbering/ chainsaw activities | District Wide | No. of field visits to sites |  |  |  |  | 10,000.00 |  |  | FSD | DA |
| 25 | Monitor activities of small scale mining companies | District Wide | No. of field visits to sites |  |  |  |  | 10,000.00 |  |  | CA | DA |
| 26 | Improvement of staff accommodation (Assembly bungalows, Teacher’s quarters, Police depot, Nurses quarters, etc.) | District Wide | No. of accommodation constructed |  |  |  |  | 100,000.00 |  |  | Works | DA |
| 27 | Construction of Police Post 3 | Subriso |  |  |  |  |  | 50,000.00 |  |  | Works | DA |
| 28 | Renovation of Agric quarters | Akutreso Wuruyie | Agric. quarters renovated |  |  |  |  | 100,000.00 |  |  | Works | DA |
| 29 | Improve upon road surface conditions (feeder roads) | District Wide | Kilometers of road improved |  |  |  |  | 200,000.00 |  |  | Works | DA |
| 31 | Facilitate the extension of telecommunication services | District Wide | No. of communities covered |  |  |  |  | 10,000.00 |  | 5,000.00 | CA | DA |
| 32 | Organize a training on fire prevention and management | District Wide | No. of training organized |  |  |  |  | 5,000.00 |  |  | NADMO | DA/ GNFS |
| 33 | Construct 10 No. teachers quarters | Akotreso, Adwenase, Samankrom | 10 No. teachers quarters constructed |  |  |  |  | 150,000.00 |  | 50,000.00 | Works | DA |
| 34 | Construction of Dormitories for Women and Children | Akrofuom | Dormitories for women and children constructed |  |  |  |  |  |  | 100,000.00 | Works | MP |
| 36 | Prepare planning schemes/ layouts for communities | District Wide | No. of planning schemes / layouts prepared |  |  |  |  | 10,000.00 |  |  | TCPD | DA |
| 37 | Embark on street naming and property addressing system | District Wide | No. of streets/ properties named |  |  |  |  | 30,000.00 |  |  | TCPD | DA |
| 38 | Organize site inspections throughout the year to control development | District Wide | No. of site inspections organized |  |  |  |  |  | 5,000.00 |  | Works | DA |
| 39 | Service and repair No. computers and accessories, photocopier and intercom annually | DA | No. of computers / accessories, etc. serviced |  |  |  |  | 30,000.00 |  |  | CA | DA |
| 40 | Support One-District-One-Factory initiative | District Wide | Amount of funds disbursed on activities |  |  |  |  | 10,000.00 |  |  | Agric | DA |
| 41 | Provision of agro-based industries for palm oil, gari, rice and cocoa processing | District Wide | No. of agro-based industries constructed |  |  |  |  | 50,000.00 |  |  | Agric | DA |
| 42 | Support planting for food and jobs programme | District Wide | Amount of funds disbursed on programme |  |  |  |  | 10,000.00 |  |  | Agric | DA |
| 43 | Skill training for the youth in income generation activities | District Wide | No. of youth trained |  |  |  |  | 10,000.00 |  |  | SW& CD | DA |
| 44 | Organize education programs on natural and man-made disasters | District Wide | No. of programmes organized |  |  |  |  | 10,000.00 |  |  | NADMO | DA |
| 45 | Construct CHPS Compound | Bonkro and Edwinase | CHPS Compound constructed |  |  |  |  | 150,000.00 |  |  | Works | DA |
| 46 | Renovation of CHPS Compounds/ health facilities | District Wide | CHPS Compounds and Health facilities renovated |  |  |  |  | 100,000.00 |  |  | Works | DA |
| 47 | Support HIV/AIDS programs (MSHAP) | District Wide | Amount of funds disbursed for HIV/AIDS programs |  |  |  |  | 20,000.00 |  |  | CA | DA |
| 48 | Support District response initiative on malaria control programs | District Wide | Amount of funds disbursed for malaria control program |  |  |  |  | 10,000.00 |  |  | DHD | DA |
| 49 | Support mental health care | District Wide | Amount of funds disbursed for mental health care |  |  |  |  | 10,000.00 |  |  | DHD | DA |
| 50 | Support family planning program | District Wide | Amount of funds disbursed for family planning |  |  |  |  | 5,000.00 |  |  | DHD | DA |
| 51 | Provide maternal waiting homes | District Wide | No. of maternal waiting homes provided |  |  |  |  | 20,000.00 |  |  | DHD | DA |
| 52 | Renovation of New Edubiase of Selected Facilities at New Edubiase | New Edubiase | No. of additional infrastructure provided |  |  |  |  | 75,000.00 |  |  | Works | DA |
| 53 | Support national immunization program | District Wide | Amount of funds disbursed |  |  |  |  | 5,000.00 |  |  | DHD | DA |
| 55 | Organize hygiene education in schools and communities | District Wide | No. of participant in schools and communities visited |  |  |  |  |  | 5,000.00 |  | DHD | DA |
| 56 | Construction of classroom Blocks | Kramokrom Avornyo, Apagya, Wuruyie, Atobiase, | 10 No. classroom blocks constructed | ` |  |  |  | 200,000.00 |  | 200,000.00 | Works | DA |
| 57 | Enhance Ghana School Feeding Program | District Wide | Amount of funds disbursed to beneficiary schools |  |  |  |  | 20,000.00 |  |  | CA | DA |
| 58 | Supply of dual desk furniture for schools in the area | District Wide | No. of dual desk supplied |  |  |  |  | 50,000.00 |  |  | DED | DA |
| 60 | Support girl-child education | District Wide | No. of girl-child supported |  |  |  |  | 10,000.00 |  |  | DED | DA |
| 61 | Support the activities of District Oversight Committee (DEOC) | District Wide | No. of DEOC activities supported |  |  |  |  | 10,000.00 |  |  | DED | DA |
| 62 | Support Science, Technology, Mathematics, Education (STME) clinic | District Wide | No. of students supported in STME |  |  |  |  | 10,000.00 |  |  | DED | DA |
| 63 | Support sports development | District Wide | No. of sports activities supported |  |  |  |  | 10,000.00 |  |  | DED | DA |
| 64 | Education fund disbursed to needy students | District Wide | No. of students supported |  |  |  |  | 25,000.00 |  |  | CA | DA |
| 65 | Rehabilitation of 2 No. Schools | District Wide | 2No. schools renovated |  |  |  |  | 100,000.00 |  |  | Works | DA |
| 66 | Provide for fumigation and sanitation | District Wide | Area fumigated and sanitized |  |  |  |  | 328,000.00 |  |  | Env’tal | DA |
| 67 | Clearing of final dump sites | District Wide | Number of dump sites cleared |  |  |  |  | 60,000.00 |  |  | Env’tal | DA |
| 68 | Organize training on GIS | District Wide | No. of participants trained |  |  |  |  | 10,000.00 |  |  | TCPD | DA |
| 69 | Provide disaster relief items | District Wide | No. of relief items distributed |  |  |  |  | 50,000.00 |  |  | NADMO | DA |
| 70 | Form Disaster Volunteer Groups | District Wide | No. of groups formed |  |  |  |  | 5,000.00 |  |  | NADMO | DA |
| 71 | Build capacity of staff, assembly members, town and area council members, etc. | District Wide | No. of participants trained |  |  |  |  |  |  | 50,000.00 | CA | DA |
| 72 | Maintain and repair official vehicle and Assembly grader | DA | Amount of funds disbursed in maintaining official vehicles and grader |  |  |  |  | 70,000.00 |  |  | CA | DA |
| 73 | Organize public fora and disseminate relevant information to stakeholders | District Wide | No. of public fora organized |  |  |  |  | 15,000.00 |  |  | CA | DA |
| 74 | Monitor and Evaluate projects | District Wide | No. of projects monitored/ evaluated |  |  |  |  | 50,000.00 |  |  | DPCU | DA |
| 75 | Procure sanitary/cleaning materials, logistics and equipment, office supplies etc | DA | Amount of funds disbursed in the procurement |  |  |  |  | 20,000.00 |  |  | CA | DA |
| 76 | Procure insurance for official vehicles | DA | No. of vehicles insured |  |  |  |  |  | 10,000.00 |  | CA | DA |
| 77 | Purchase building materials for community initiated projects | DA | Quantity of building materials purchased |  |  |  |  | 158,000.00 |  |  | CA | DA |
| 78 | Procure street light bulbs for distribution | DA | No. of street light bulbs procured |  |  |  |  | 60,000.00 |  |  | CA | DA |
| 79 | Prepare District Medium Term Development Plan (2018-2021) and Annual Action Plans | DA | DMTDP prepared |  |  |  |  | 30,000.00 |  |  | DPCU | DA |
| 80 | Ensures effective implementation of DPCU activities | DA | No. of DPCU activities implemented |  |  |  |  | 10,000.00 |  |  | DPCU | DA |
| 81 | Organize Official Day Celebrations | DA | Amount of funds disbursed |  |  |  |  | 55,000.00 |  |  | CA | DA |
| 82 | Organize DISEC Meetings | DA | No. of DISEC meetings organized |  |  |  |  | 10,000.00 |  |  | CA | DA |
| 83 | Support Town and Area Council in their activities | District Wide | No. of Town and Area Council activities supported |  |  |  |  | 4,000.00 |  |  | CA | DA |
| 84 | Support paupers, children and physically challenged | District Wide | No. of paupers, children and physically challenged persons supported |  |  |  |  | 15,000.00 |  |  | SW&CD | DA |
| 85 | Organize mass educational programs and workshops | District Wide | No. or participants at mass educational programs/ workshops |  |  |  |  | 3,000.00 |  |  | SW&CD | DA |
| 86 | Register Persons With Disabilities(PWDs) | District Wide | No. of persons registered as PWDs |  |  |  |  | 47,000.00 |  |  | SW&CD | DA |
| 87 | Undertake activities on LEAP program | District Wide | No. of activities undertaken on LEAP |  |  |  |  | 10,000.00 |  |  | SW&CD | DA |
| 88 | Supervise community initiated projects | District Wide | No. of projects supervised |  |  |  |  | 12,000.00 |  |  | Works | DA |
| 89 | Publish Assembly activities and gazette by-laws | DA | No. of activities published and by-laws gazetted |  |  |  |  | 2,500.00 |  |  | CA | DA |
| 91 | Ensure minor repair/ maintenance of office machines and furniture | DA | Amount of funds disbursed to repair and maintain office machines/ furniture |  |  |  |  | 10,000.00 | 5,000.00 |  | CA | DA |
| 93 | Procure office facilities and furniture for the Assembly office every year | DA | No. of furniture and facilities procured |  |  |  |  | 20,000.00 |  |  | CA | DA |
| 96 | Engage consultants to train relevant staff of the Assembly and Assembly members | DA | No. of staff and Assembly members trained |  |  |  |  |  |  | 51,432.00 | CA | DA |
| 97 | Screening of food vendors | District Wide | No. of food vendors screened |  |  |  |  | 15,000.00 |  |  | Env’tal | DA |
| 98 | Implement MPs constituency programmes and projects annually | District Wide | No. of programmes implemented |  |  |  |  | 300,000.00 |  |  | MP | DA |
| 99 | Support Traditional Authorities Allowance | District Wide | Amount of funds disbursed to TA |  |  |  |  |  | 10,000.00 |  | CA | DA |
| 100 | Provide legal/security expenses of the Assembly | DA | Amount of funds disbursed for legal/ security expenses |  |  |  |  | 15,000.00 |  |  | CA | DA |
| 101 | Maintain adequate security in the District annually | District Wide | No. of activities undertaken to maintain security |  |  |  |  | 15,000.00 |  |  | CA | DA |
| 102 | Provision of potable water | District Wide | No. of people with access to potable water |  |  |  |  | 25,000.00 |  |  | CA | DA |
| 103 | Construction of public toilets(KVIP/WC) | New Edubiase market | Public toilets constructed in New Edubiase market |  |  |  |  | 150,000.00 |  |  | CA | DA |
| 104 | Organize sensitization programs on the local radio stations and community information centers | DA | Organize sensitization programs on the local radio stations and community information centers organized |  |  |  |  |  |  | 6,000.00 |  |  |
| 105 | Report activities of the Assembly through quarterly and annual progress reports | DA | quarterly and annual progress reports prepared and submitted |  |  |  |  |  |  | 5,000.00 |  |  |