Contents

ACKNOWLEDGEMENT	4

EXECUTIVE SUMMARY	5

CHAPTER ONE	7

DISTRICT PROFILE	7

1.1: GEOGRAPHICAL LOCATION	7

1.2: POPULATION SIZE AND GROWTH RATE	8

1.3:  HEALTH SERVICE DELIVERY	9

1.4: SCHOOLS	10

1.5: ORGANIZATIONAL STRUCTURE	10

1.6: ADMINISTRATIVE STRUCTURE [POLITICAL]	10

1.7: ADMINISTRATIVE STRUCTURE [TRADITIONAL]	11

1.8: DEPARTMENTS IN THE DISTRICT	11

1.9. COMMUNICATION AND UTILITIES	11

1.10:  SOCIO-ECONOMIC ACTIVITIES	12

1.11:  SOCIO-CULTURAL ACTIVITIES	12

CHAPTER TWO	13

PROGRAMME OF WORK	13

2.1: HEALTH SECTOR OBJECTIVES	13

2.2: SUMMARY OF KEY PRIORITIES	13

2.3: SUMMARY OF KEY ACTIVITIES IMPLEMENTED BY OBJECTIVES	14

CHAPTER THREE	30

KEY PERFORMANCE INDICATORS	30

3.1: Maternal Health	30

3.2: Adolescent Health Services	41

3.3: Family Planning (FP)	44

3.4: Child Health	46

3.5: Nutrition	49

3.6: Clinical Care Services	52

3.6: Community-Based Health Planning and Services (CHPS)	57

CHEAPTER FOUR	58

CHALLENGES AND RECOMMENDED MITIGATIVES	58

Challenges and Way Forward	58

Appendix	60

A: Holistic Assessment Indicators and Scores	60

B: Sector wide Indicators	64

# ACKNOWLEDGEMENT

The Ghana Health Service acknowledges the participation and support of all stakeholders in the successful implementation of Health Service delivery in Adansi South district. Our special thanks go to all Health Partners in the district for their immerse contributions towards the achievement of 2019 Health Sector Objectives in the district.

We also appreciate the following;

- Regional Director of Health Services, Deputy Directors, Programme Heads and Staff of Regional Health Directorate for their Supervisory roles

- The honorable Chief Executive of Adansi South District Assembly for his abled Leadership

- The Honorable Member of Parliament of New Edubiase Constituency

- The Medical Superintendent, Management and Staff of New Edubiase Government Hospital

- Subdistrict heads and entire Staff of Akutreso and Ataase Subdistricts

Finally, we wish to congratulate the District Health Management Team, Programme heads and entire Staff of the District Health Directorate for strong team work and commitments towards this achievement

# EXECUTIVE SUMMARY

The District Health Directorate has the primary mandate to ensure a healthy population by providing quality healthcare services to all people living in the District. This priority is achieved through a seamless access to health services from community level to the district level.

The District Health directorate 2019 annual report is organized into five chapters. Chapter one describes the profile of the district. Chapters two and three explain the 2019 Programme of Work (PoW) and key performance indicators as against targets respectively. Chapter four describes the main challenges faced during the year and the strategies to address these challenges in the coming years. The final chapter outline the Holistic assessment tool scoring the district against the set target.  Sector wide indicator figures are covered in the Annexes.

In June 2018, Adansi Akrofoum district was carved from Adansi South district taken away two subdistricts, two health facilities, three CHPS zones and 31% of the district population.

In 2019, thirty (30) functional CHPS zones were sustained and strengthened across the district. Out of this total number, four (4) CHPS zones have compounds as against three (3) in 2018. An improved stakeholders’ involvement contributed enormously towards this achievement.

The strength of the Health Sector workforce slightly improved, especially in the area of nursing and midwifery. Doctor- Population ratio also improved from 1:94,224 to 1: 48,394 as one additional Medical Officer was posted into the district in the year under review. However, none of the Human Resource (HR) indicators met the target. This is not encouraging for the Health Service, particularly at a time when it is positioning itself for universal coverage.

The OPD per Capita has been stagnating since 2017 with per capita of 0.6. Out of the total OPD attendance 83% were insured as compared to 84% in 2018.

As efforts to ensure improved maternal and neonatal health continued, there was an increase in the proportion of pregnant women achieving the minimum of four (4) antenatal care (ANC) visits in 2019. Approximately, 81% of pregnant women made at least 4th ANC visits in 2019. Teenage pregnancies for the first time in the district, saw a decline in the year under review. The supervised delivery rate improved from 33% in 2018 to 39% in 2019. Maternal mortality ratio saw a significant improvement from 159/100,000 live births in 2018, to 66/100,000 live births in 2019. Family Planning coverage stagnated at 31%. These improvements in maternal healthcare although not conclusive, could be a reflection of the increase in critical workforce, particularly midwives in the district.

Improvement in childhood immunization is measured using Penta-3 as proxy. District average of Penta-3 coverage decreased by 1.91% from 2018 rate.

Meanwhile, the Service suffered the repercussions of lack of service funds from the Government of Ghana and denied majority of its essential service activities that were scheduled to be implemented during the year under review.

Mr. Daniel Yeboah

District Director of Health Services

Adansi South

# CHAPTER ONE

## DISTRICT PROFILE

This chapter explains the profile of the district taken into account the population distributions, health facilities and stakeholders in health

### 1.1: GEOGRAPHICAL LOCATION

The Adansi South District is one of the oldest districts among the forty-six (46) administrative districts in the Ashanti Region. It lies in the southernmost part of the region. It is boarded by many districts, including districts from two regions; Central and Eastern. In 2018, Akrofoum district was carved out form Adansi south district.

The district has a characteristically high ethnically mixed population dominated by Adansis, Ewes, Fantis, Akuapims, and Ga-Adangbes with an attendant cultural variability especially in attitudes and response to health risk behaviour. Also, the settlement determinants favour hamlets and cottages phenomenally at the expense of urbanization. The district stretches from one end to the other to a distance of 94 km.

### 1.2: POPULATION SIZE AND GROWTH RATE

According to Ghana Statistical Service and projections from the 2010 Population and Housing census, the population for the district in 2020 is 98,696. The annual growth rate in the district is about 1.97%. Below is the population distribution by sub-district;

Table 1.1: Sub district population distribution, 2016-2018

| Sub-district | 2017 | 2018 | 2019 (2.68%) | 2020 (1.97%) |
| --- | --- | --- | --- | --- |
| AKUTRESO | 15721 | 16094 | 16528 | 16854 |
| ATAASE | 39435 | 39435 | 41461 | 4228 |
| NEW EDUBIASE | 36903 | 37780 | 38800 | 39564 |
| TOTAL | 92059 | 93309 | 96789 | 98696 |

Table 1.2: Children 0 – 11 months (4%) for EPI and Expected Pregnancies (ANC)

| Sub-district | 2017 | 2018 | 2019 | 2020 |
| --- | --- | --- | --- | --- |
| AKUTRESO | 629 | 644 | 661 | 674 |
| ATAASE | 1577 | 1577 | 1658 | 1691 |
| NEW EDUBIASE | 1476 | 1511 | 1552 | 1583 |
| TOTAL | 3682 | 3732 | 3872 | 3948 |

Table1.3:  Children 6-11 months and 12-59 months for Vitamin A supplementation

|  | 6-11 moths (2%) |  |  |  | 12-59 months (14.5%) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-district | 2017 | 2018 | 2019 | 2020 | 2017 | 2018 | 2019 | 2020 |
| AKUTRESO | 314 | 322 | 331 | 337 | 2280 | 2334 | 2397 | 2444 |
| ATAASE | 789 | 789 | 829 | 846 | 5718 | 5718 | 6012 | 6130 |
| NEW EDUBIASE | 738 | 756 | 776 | 791 | 5351 | 5478 | 5626 | 5737 |
| TOTAL | 1841 | 1866 | 1936 | 1974 | 13349 | 13530 | 14034 | 14311 |

Table1.4: WIFA (24%) of the total population for Family Planning

| Sub-district | 2017 | 2018 | 2019 | 2020 |
| --- | --- | --- | --- | --- |
| AKUTRESO | 3773 | 3863 | 3967 | 4045 |
| ATAASE | 9464 | 9464 | 9951 | 10147 |
| NEW EDUBIASE | 8857 | 9067 | 9312 | 9495 |
| TOTAL | 22094 | 22394 | 23229 | 23,687 |

### 1.3:  HEALTH SERVICE DELIVERY

The district has been demarcated into thee (3) sub-districts. This is to facilitate the delivery of health services. There is one (1) hospital, four (2) health centres, one (1) maternity home and four (4) Community-based Health and Planning Services (CHPS) compounds.

At the moment, there are over 200 communities and hamlets in the district with eighty-six (86) outreach points.

Table 1.5: Names of health facilities and location

| Sub-district | Health Facility | Ownership | Location |
| --- | --- | --- | --- |
| Ataase | Ataase Health Centre Atwereboana CHPS Hwidiem CHPS Obonsu CHPS | Government Government Government Government | Ataase Adansi Atwereboana Hwidiem Obonsu |
| Akutreso | Akutreso Health Centre Tweapease CHPS | Government Government | Akutreso Tweapease |
| New Edubiase | New Edubiase Hospital Hill top Maternity Home | Government Private | New Edubiase Atobiase |

Outreach sites

| Sub-district | Number of Outreach site |
| --- | --- |
| Akutreso | 17 |
| Ataase | 46 |
| New Edubiase | 23 |
| Total | 86 |

A critical look at the positioning of these facilities, it is evident that few communities have relatively high access to Health services. There are a whole lot of communities and hamlets that have challenges with health care accessibility due to the bad nature of roads in the district.

The inhabitants seek health services through the following network of health facilities;

Table 1.6: Types of health facility

| FACILITY | NUMBER |
| --- | --- |
| Hospitals | 1 |
| Health Centres | 2 |
| Private Maternity Homes | 1 |
| Functional CHPS compounds | 4 |
| Total | 8 |

Also prevalent in the district are Community chemical sellers, Traditional Healers, Herbalists and Homeopathic practitioners.

### 1.4: SCHOOLS

There are 191 registered schools in the district consisting of 146 pre-schools and Basic schools, 43 Junior high schools, and 2 Senior high school. Below is the number of schools per sub-district

Table 1.7: Number of schools

| Sub district | Number of schools |
| --- | --- |
| Akutreso | 45 |
| Ataase | 96 |
| New Edubiase | 91 |

### 1.5: ADMINISTRATIVE STRUCTURE [POLITICAL]

The District Chief Executive is the political head with the District Coordinating Director as Administrative head and advisor to the district Chief Executive. Among the ex-officio members of the Assembly are various heads of decentralized departments representing the various district sector ministries. There are also about thirty (30) Assembly members who help in organizing or mobilizing people for development in the various communities.

### 1.6: ADMINISTRATIVE STRUCTURE [TRADITIONAL]

There is one Traditional Area, named Edubiase Traditional Area with New Edubiase as its capital.

### 1.7: DEPARTMENTS IN THE DISTRICT

Some of the decentralized departments in the District are; Ghana Education Service [GES], Social Welfare, Community Development, National Commission for Civic Education, Ghana Health Service, Ghana Ambulance Service, Internal Revenue Service, Fire Service, Ministry Of Food and Agriculture [MOFA],  Judicial Service, Forestry Department, Stool Lands, Ghana Police Service, Feeder Road, National health Insurance Authority  etc.

### 1.8. COMMUNICATION AND UTILITIES

#### 1.8.1 Water and sanitation

The main source of water supply in the district capital is pipe-borne water. However, surrounding communities depend heavily on harvested rainwater, boreholes, hand-dug wells and streams. Access to portable water is therefore irregular and seasonal in nature. During the dry season, rivers and streams dry up and water supply becomes a challenge. Sanitary facilities for both liquid and solid waste disposal are also inadequate in most part of the district.

#### 1.8.2 Road networks

The district has a bad road network, which reduces socio-economic activities.  The feeder roads into various part of the district are not tarred and many are in deplorable state. Many branch roads to the rural communities and hamlets become un-motorable during the raining seasons.

#### 1.8.3 Transportation

The bulk of transportation is provided by the private sector. It is however, fairly easy to travel from the district capital, New Edubiase to other parts of the region and beyond.

#### 1.8.4 Telecommunications and electricity

Cellular phones are the main means of Telecommunication. All the major towns in the district have been connected to the national electricity grid. Over 90% of the population therefore enjoy electric power. However, the power supply has been irregular and often fluctuating in intensity.

### 1.9:  SOCIO-ECONOMIC ACTIVITIES

There are four major occupations in the district, namely; Agriculture, Mining, Commerce, and Civil / Public Service.

Most people are engaged in farming and lumbering/sawmilling. The abundant rainfall makes rice and cocoa cultivation attractive and the district is one of the main producers. Plantain, cassava and cocoyam are produced both on small scale and commercial quantities. Other economic activities include illegal mining, lumbering and sawmilling, game hunting, palm wine tapping and Akpeteshie distilling. Trading, hairdressing, dressmaking carpentry and auto mechanics are also dominating.

### 1.10:  SOCIO-CULTURAL ACTIVITIES

It is a taboo to eat fish from a river in the Edubiase Township. Taboo days are Akwasidae most inhabitants do not engage in farming activities during this day. Goat rearing in Edubiase and some other communities are also forbidden. Adansiman is a part of the Ashanti tradition and they practice matrilineal inheritance.

# CHAPTER TWO

## PROGRAMME OF WORK

### 2.1: HEALTH SECTOR OBJECTIVES

This annual report provides comprehensive service operations and performances during the year, as well as comparative trend analysis of activities undertaken under the four (4) Health Sector Objectives (HSOs).

The Health Sector Objectives which the Service assesses its performance are:

- To ensure a sustainable, affordable, equitable easily accessible health care services (universal health coverage)

- To reduce morbidity and mortality, intensify prevention and control of non-communicable diseases

- To enhance efficiency in Governance and management

- To intensify prevention and control of communicable disease and ensure the reduction of new HIV/AIDS and other STI, especially among the vulnerable group

### 2.2: SUMMARY OF KEY PRIORITIES

The Health Objectives require certain priority actions by the district Health Directorate. These priorities have been broadly categorized under the four main Ghana Health Service Objectives. Below is a summary of the priorities for year 2020.

HO1: To ensure a sustainable, affordable, equitable easily accessible health care services

- Strengthen collaboration with stakeholders to improve service delivery

- Improve institutional deliveries

- Improve family Planning services and commodity management

- Strengthen human resource for health

- Scale-up CHPS implementation

HO2: To reduce morbidity and mortality, intensify prevention and control of non-communicable diseases

- Improve Maternal and Child Health services

- Strengthen adolescent health services

- Reduce the burden of Non-communicable disease

HO3: To Enhance efficiency in Governance and management

- Improve monitoring and supervision at sub-districts and CHPS zones

- Improve Data management at all levels

- Improve customer care

HO4: To Intensify prevention and control of communicable disease and ensure the reduction of new HIV/AIDS and other STI, especially among the vulnerable group

- Strengthen Disease surveillance

- Improve Expanded Programme on Immunization coverage

- Improve Tuberculosis activities

### 2.3: SUMMARY OF KEY ACTIVITIES IMPLEMENTED BY OBJECTIVES

HO1: To ensure a sustainable, affordable, equitable easily accessible health care services

#### 2.3.1: Strengthen collaboration with stakeholders

The District Health Management Team (DHMT) through its Strong lobbying and liaising skills collaborated with under listed stakeholders and partners in the year under review:

The regional Health Directorate

The regional health directorate through its human resource unit posted twenty- eight (28) categories of staff to the district. Notable among them was one (1) medical officer bringing the total number of doctors to three (3). Table 2.1 depicts cadre of staff posted into the district in 2020;

Table 2.1

| Administrative Manager | 2 |
| --- | --- |
| Enrolled Nurse | 1 |
| Community Health Nurses | 5 |
| Community Health Nurse (Diploma) | 4 |
| Staff Midwife | 4 |
| Nursing Officer | 1 |
| Accountant | 2 |
| Optician | 1 |
| Senior Pharmacist | 1 |
| Executive Officer | 1 |
| Medical Officer | 1 |
| Physician Assistant | 2 |
| Senior Certified Anesthetic | 1 |
| Mortuary Attendant | 2 |
| Total | 28 |

In addition to the above, the regional health directorate supplied the district health directorate with a motorbike and number of COVID-19 Personal Protective Equipment (PPE), Veronica buckets with stand, Basin, liquid soaps, tissue papers and hand sanitizers. Refer to appendix 1 for details. Furthermore, the regional health directorate supplied thirty (30) home visit packs to support home visit activities in the CHPS level.

Adansi South District Assembly

The year 2020 was challenging in the health sector due to the novel coronavirus pandemic. The district recorded its first case in April 2020. Before the onset of the index case, the district assembly together with the health directorate formed the District public health emergency committee chaired by the District Chief Executive (DCE) to strategize towards the fight against the novel disease in the district. The Adansi South District Assembly which is the major stakeholder in the district supported the directorate with funds and number of equipment in the fight against the pandemic. In the area of CHPS construction, the district assembly constructed staff accommodation at Menang CHPS compound in the year review.

Office of the Member of parliament (MP), New Edubiase constituency

Mr. George Oduro, the honorable member of parliament for New Edubiase Constituency donated a motorbike to the district health directorate to support the community outreach services.  The honorable member also supported the new staff posted to the district with rent advance subsidy. Mr. Oduro also supported the directorate with the NHIA funds for health development to continue Bepoase CHPS compound construction and purchase of workstation for the district health directorate human resource unit.

Marie Stopes International

Since the year 2015, the district has not met its target of 40% for the family planning acceptor rate. This may partly be due to inability of Community Health Nurses to visit clients in their various communities and shortage of some long-term commodities. In view of this, Marie Stopes International has been supporting the district since 2019 to provide long-term permanent and reversible family planning methods in the district hospital and communities.

Other Benevolent Organizations

As a social obligation, the Seventh Day Adventist Church (SDA) and The Church of Pentecost donated various COVID-19 items included veronica buckets and stand, basins, liquid soaps, tissue papers and hand sanitizers to the district health directorate and hospital to help in the fight against COVID19 pandemic.

2.3.2: Scale up CHPS implementation

The Bepoase CHPS compound construction which was started in 2018 under the MP’s support for community-initiated projects continued as scheduled. Wiring and ceiling were done with water and staff accommodation yet to commence. Other CHPS compounds with various levels of completion are as follows; The Amuduroase community also provided a room for the Community Health Nurse in order to facilitate her work. Furthermore, Menang CHPS compound which was under construction had its staff accommodation constructed. The facility is yet to be provided with other amenities.

Table 2.2: Uncompleted CHPS compounds, 2020

| No. | Sub-district | Community | Level of Completion | Financier |
| --- | --- | --- | --- | --- |
| 1 | Akutreso | Tonkoase II | Painting | Community |
| 2 | Ataase | Bepoase | Water, electricity, staff accommodation | MP |
| 3 | New Edubiase | Menang | Plastering, electricity water | DA |

#### 2.3.3: Improve family Planning services

- Modern family planning acceptance had not been able to meet its annual targets in the past three years. Among others, data capturing challenges, shortage of preferred commodities, inaccessibility, poverty and misconceptions accounted for this decline. The directorate tasked all family planning service providers to re-register all their clients who were on the long-term family planning methods for each month. Data validations were conducted on each month to check family planning data accuracies and performance against target. Monitoring and supportive supervision were also done in various CHPS zones to check the availability of family planning commodities at both static and outreach sites. Chemical sellers were tasked to submit reports on family planning commodities sold to respective clients during each month. The Regional Health Directorate also trained ten (10) family planning service providers on Sayana press. Th district also benefited from out of public sector strengthening program organized by Marie Stopes. In collaboration with Marie Stopes International, family planning campaigns were organized in some hotspot communities.

HO2: To reduce morbidity and mortality, intensify prevention and control of non-communicable diseases diligence

#### 2.3.4: Improve Maternal and Child Health services

##### 2.3.4.1: Maternal and Neonatal deaths audit

The two maternal deaths which occurred during the year were audited and cause of death identified. The main cause of the maternal deaths was Pre-eclampsia. The team also audited twenty-six perinatal deaths to identify causes and strategies to prevent future occurrence.

The district implemented cost-effective interventions, which were proven to address maternal and neonatal mortalities. Some of these interventions included; quality antenatal care providing a comprehensive package of health and nutrition services, promoting access to family planning services, access to skilled health personnel at delivery, availability of basic and comprehensive emergency obstetric care services and training of Midwives and other health professionals during family heath meetings.

##### 2.3.4.2: The maternal and child health record book training

The Maternal and Child Handbook is a booklet containing information on safe pregnancy, delivery, postnatal and child health and serves as a health record. It ensures continuity of care and provides health education to parents. As such it has proven to be an effective tool in promoting and protecting the health of mothers and children.

In the last quarter of 2019, the district Nutrition and Reproductive and Child health units were trained on the new Maternal and child health booklet by the Ghana health service and JICA. The district also trained all community health nurses, midwives and other health professionals who come into contact with Antenatal, Postnatal and Child welfare clinic clients in the district to enable these health workers to provide quality health care services. In all eighty-six (86) health professionals were trained in four batches. Though the training began in the last quarter of 2019, not all the intended staff were trained because they were grouped into smaller units and hence the remaining number who were not trained in 2019 had their training in January 2020.

The training which was largely sponsored by Japan International Cooperation Agency (JICA) aimed at improve the maternal and child health service delivery and outcomes by ensuring continuum of care and proper recording of the mother and child health care. The book is designed to link the health records of mother to her child from pregnancy till the child attains the age of five. It also addresses issues such as nutrition, growth monitoring and promotion, and health education in a more focused and illustrative way.

2.3.4.3: MCHRB Monitoring

The district team made up of Nutrition Officer, Public Health Nurse and a Midwife conducted the First round of monitoring and supportive supervision to some CHPS Zones in January and February 2020. The second round planned monitoring was halted by the COVID-19 situation. Among others gaps identified during the monitoring were; incomplete filling of the booklet, non-usage of infantometer, among others.

##### 2.3.4.4: Growth Monitoring and Promotion

This is an on-going programme carried out in the district to assess the growth of children from 0 - 59 months. It also helps to identify severe malnutrition cases for early intervention in order to reduce malnutrition prevalence.

During these sessions, weight and height compared with their respective ages are checked. Those that fall short are given appropriate counselling and where the need be some are referred to the necessary quarters for timely and appropriate intervention.

Again, children are assessed on their developmental milestones to see if they are able to exhibit the required signs for their particular age which helps to know mainly the brain coordination.

##### 2.3.4.5: Child Health Promotion Month

The Child Health Promotion celebration takes place in May every year by the Ghana Health Service as part of effort to improve on efficient service delivery, quality of essential preventive service and create awareness of child health issues. The 2020 annual Child Health Promotion Week took place from 11th to 15th May, 2020 under the theme “Promoting newborn and child health services in the wake of the COVID-19 pandemic".

Taking into account social distancing/avoiding crowding, hand hygiene, respiratory hygiene and other recommended precautionary measures, activities which took place included; Growth monitoring Immunizations, Birth registration, Vitamin A supplementation, Nutrition counselling, promoting use of ITNs, promoting antenatal, supervised delivery services and postnatal care for mother and newborn, Appropriate umbilical care using chlorhexidine 7.1% gel, Breastfeeding and Prevention of COVID-19.

##### 2.3.4.6: Breastfeeding Programme

Breastfeeding gives children the best start in life. Breastfeeding is a cornerstone of children’s survival, nutrition and early development. Breastfeeding not only provides children with the best start in life, it also benefits maternal health, protects against non-communicable diseases and contributes to environmental sustainability.

Mother who delivers at the health facility were monitored to put their babies to breast within the first 30 minutes after delivery unless clinically there is a problem. Again, all mothers who pass through the health facilities and outreach centers were advised to breastfeed their children exclusively for 6 months, initial timely complementary feeding at 6 months and then ensure that the children breastfeed till 2years and beyond.

##### 2.3.4.7: Nutrition Rehabilitation programme

Nutrition Rehabilitation seeks to help children who are malnourished to recover or catch up quickly with lost or unbalanced nutrients and also treat other infections. Therefore, severely malnutrition cases detected are referred to the MCHH rehabilitation center where they are to be rehabilitated or sometimes referred to Fomena when the situation is quite moderate but unfortunately mothers refuse to go due to transportation and the distance from the district to Kumasi. Therefore, clinicians in the hospital do their part and mothers or caregivers are then counseled nutritionally upon discharge and some mothers were given fortified blended flour to prepare for the child.

##### 2.3.4.8:  Diet Related Diseases

A special clinic day has been set for all patients with any of the diet related diseases. This clinic is organized every week (Wednesdays and Fridays), where patients are being advised on their diet, given their medication and encouraged to exercise.

##### 2.3.4.9: MICRO NUTRIENTS DEFICIENCY CONTROL

###### 2.3.4.9.1: Anemia in Pregnancy

Though anemia continues to be a key challenge in terms of micronutrient deficiency among pregnant women and has severe consequences for the mother and fetus, several activities were done to prevent iron deficiency anemia especially in children, pregnant women and women in fertile age at the district. activities include, iron supplementation, counselling on diet, deworming and blood transfusion when at the extreme.

###### 2.3.4.9.2: Vitamin A Deficiency Control (VAD)

Vitamin A Deficiency (VAD) is said to contribute to the prevailing high under-five morbidity, mortality and poor vision in all age groups. There is therefore the need for Vitamin A supplementation especially in children. Supplementation took place during Routine Outreach programs, static clinics, home visits, school health, NIDs and EPI Mop ups. Capsules were given at 6 months till child attains 5 years at 6 monthly intervals.

HO3: To Enhance efficiency in Governance and management

#### 2.3.5: Monitoring and supervision

The district conducted four (4) rounds of integrated supervisions to the sub-districts in the year under review. These supervisions were Facilitative Support Visits (FSVs), supported by World bank through Maternal and Child Health Nutrition project (MCHNP) and integrated supportive supervision. Facilitative Support Visits afforded the district and sub-districts’ staff the opportunity to support lower level staff on public health services.

In addition to integrated supervision, Programme specific monitoring and supervisions also took place in the year under review. These were, Neglected Tropical Diseases (school deworming, onchocerciasis programme), Child health promotion month, Combined maternal and child health record booklet, Girl Iron Folate Tablet distribution, Primary school long lasting Insecticide Net distribution, Tuberculosis programme, and Maternal and child health programmes. Details of each program outlined in units’ specific reports.

The sub-districts management team also conducted three (3) supervisions to CHPS Zones and CHPS Compounds in their respective sub-districts. The District Health Management Team (DHMT) joined the Subdistrict Health Management Team (SDHMT) during the facility and zonal supervisions. The team used the opportunity to meet some opinion leaders in the communities to strengthen Community outreach programmes.

Key findings from the supervisions were lack and faulty weighing scales, lack of benches and tables, poor data recording, lack of appropriate registers and untrained health personnel.

#### 2.3.6: Community participation and involvement

##### 2.3.6.1: Community Health Management Committee Meetings on MCHNP/CHPS

Quarterly Community Health Management Committee (CHMC) meetings were organized in all the thirty (30) CHPS zones in the district. Community Health Officers (CHOs) used the opportunity to discuss health chanllenges in their respective communities with the community leaders and also asked for their support in health service delivery. Due to the social gathering restrictions as a result of COVID-19 most CHOs were not able to organize CHMC meetings during the second quarter of the year. Table below described the details;

Table:2. 3: CHMC meetings held

| Subdistrict | No. of zones | No. CHMC meetings |
| --- | --- | --- |
| Ataase | 16 |  |
| Akureso | 5 |  |
| New Edubiase | 9 |  |
| Total | 30 |  |

##### 2.3.6.2:  Community Durbar

The district planned to organize Forty (40) community durbars. However, restriction of social gathering as a result of COVID-19 obstructed the activities.  Community health officers were instructed to use all virtual means especially the Community Information Centres (CIC) to reach community members with health education.

#### 2.3. 7: Health Information management

The Dhims 2 is the health sector reporting portal developed by the Centre for Health Information Management (CHIM). All districts report directly to the national level through this internet-based portal. All health facilities in the district have access to this platform and report directly to the national through the district and the.

In order to reduce the incidences of inaccuracy, incompleteness and untimely data submissions, daily DHIMS2 monitoring took place throughout the year.

The District DHIMS2 administrator periodically managed all inactive DHIMS2 user accounts to ensure all time access. The district also conducted on-site training for new DHIMS2 users during the year under review.

Finally, health facilities received quarterly DHIMS2 feedback on report completeness, accuracies and timelines.

#### 2.3.8: Human Resource for Health

The Human Resource department organized 2020 promotion exercise which saw to the interviewing of twenty-three (23) candidates. The results of the interview exercise were sent to the appropriate quarters with the expectation of possible promotion to their next grades.

During the year, the district was privileged to have twenty-eight (28) newly posted staff to support in various field ranging from Medicine, nursing, enrolled Nurses, allied health and other support staff. The tale below details the cadre of staff posted into the district;

| Cadre of Staff posted in | Number |
| --- | --- |
| Administrative Manager | 2 |
| Enrolled Nurse | 1 |
| Community Health Nurses | 5 |
| Community Health Nurse (Diploma) | 4 |
| Staff Midwife | 4 |
| Nursing Officer | 1 |
| Accountant | 2 |
| Optician | 1 |
| Senior Pharmacist | 1 |
| Executive Officer | 1 |
| Medical Officer | 1 |
| Physician Assistant | 2 |
| Senior Certified Anaesthetic | 1 |
| Mortuary Attendant | 2 |
| Total | 28 |

Table 2.4

The unit as part of its information dissemination exercise trained the subdistrict heads on the revised policies on posting, promotion and leave. The venue was the DHD conference hall.

The unit also organized an orientation for staff who had been posted into the district. The programme was a successful one as it ended with discussions and questions. The unit doubly used the opportunity of meeting the new entrants to fill their salary inputs and further forwarded to the regional headquarters for further processing.

The Human Resource (HR) unit in conjunction with the Accounts unit embarked on monitoring of the various facilities to ensure quality standards. The exercise unraveled administrative anomalies and helped to coach respective heads on keeping to standardized way of administration.

In the 2020, fourteen (14) staff of various cadre were also posted out including Deputy Director of Nursing Service, Biomedical scientist and a mental Health Officer. Table below categorized staff who were posted out of the district.

Table 2.5

| Categories of staff Posted Out | Number |
| --- | --- |
| Midwives | 2 |
| Enrolled Nurses | 5 |
| Community Nurses | 4 |
| Mental Health Officer | 1 |
| Biomedical Scientist | 1 |
| DDNS | 1 |
| Total | 14 |

##### 2.3.8.1: Performance Hearing

The directorate successfully conducted 2020 annual performance review on 18th February, 2021 at the District Assembly Conference hall, New Edubiase. In attendance were; Mr. Adams Abdul Salam, the honorable member of parliament for New Edubiase constituency, Mr. Opoku Mensah Alex, Assistant Director Adansi South district Assembly, Mr. David Konta, the district Director of Adansi Asokwa, Mr.  Festus Kofi Sroda, Adansi south district parent, Rev. James Safo-Adu, chairman for Local Council of Churches, Imam Salifu Ishmael, Chief Imam New Edubiase, Heads of Health Facilities, the Media and other Stake holders. The District Health Directorate, Fountain Enclave Hospital and Youth Alliance for Development vividly presented their annual reports during the meeting. The occasion was chaired by Nana Kwadwo Ekye, Benkumhene of New Edubiase Traditional Council and supported by Nana Obiri Asamoah, Sanaahene of New Edubiase Traditional Council. The District Police command among others were not in attendance.

Half-year 2020 performance hearing was also organized on 18th August, 2020 at the Conference Hall of district Assembly, New Edubiase. Various sub-districts as well as the Directorate gave twenty minutes presentation on activities and Performances.

##### 2.3.8.2: Management Meetings

Core District Health Management Team held periodic meetings to update the Office of the District Director on their implemented activities under the agreed programme of work for the year. In 2020 a total of eight (8) meetings comprising of four (4) core management and four (4) extended meeting held.

##### 2.3.8.3: Staff appraisal

All staff in the district were appraised in the year under review. The DDHS appraised DHMT members whiles sub-district heads and hospital management appraised sub-district staff and the hospital staff respectively. New midyear objectives were set for the year 2020.

HO4: To Intensify prevention and control of communicable disease and ensure the reduction of new HIV/AIDS and other STI, especially among the vulnerable group

#### 2.3.9: Integrated Disease surveillance and response

In infection and disease surveillance, it is extremely imperative to pick specimens for the laboratory confirmation. This gives an indication of the preparedness of the surveillance system.  For the past years the district is performing very well in picking up specimens for further laboratory investigations. The district was able to pick three (3) Yellow Fever, four (4) AFP, four (4) meningitis and four (4) measles cases for the year under review. For the past four years the district has not recorded any case of cholera.  This was as a result of intensive health education, adherence to hygiene etiquettes by community members, commitment by community and opinion leaders to fight against the disease among others.

Akutreso and Ataase subdistricts have been silent in picking CSM samples for the past three years. All efforts must be in place to break this chain of non-performance.

Table 2.6: IDSR

| Subdistrict | Measles |  |  | Yellow Fever |  |  | Cholera |  |  | AFP |  |  | CSM |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2018 | 2019 | 2020 | 2018 | 2019 | 2020 | 2018 | 2019 | 2020 | 2018 | 2019 | 2020 | 2018 | 2019 | 2020 |
| New Edubiase | 3 | 1 | 3 | 9 | 8 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 4 |
| Ataase | 0 | 1 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 1 | 3 | 2 | 0 | 0 | 0 |
| Akutreso | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |
| District | 3 | 2 | 4 | 12 | 10 | 3 | 0 | 0 | 0 | 1 | 7 | 4 | 0 | 3 | 4 |

#### 2.3.10: Monitoring of Tuberculosis activities

Tuberculosis (TB) is caused by a bacterium called Mycobacterium tuberculosis. The bacteria usually attack the lungs. However, the bacteria can attack any part of the body such as the kidney, spine, and brain. If not treated properly, TB disease can be fatal. Not everyone infected with TB bacteria becomes sick. As a result, two TB-related conditions exist; latent TB infection and TB disease. Both latent TB infection and TB disease can be treated.

In the year under review, the district conducted Tuberculosis Case detection and management monitoring in two (2) Health centers and four (4) CHPS compounds to abreast staff with the skills to detect, control and manage Tuberculosis cases in their various health facilities. During the monitoring exercise some of the observations made were;

- Most participants were not familiar with the Tuberculosis reporting form

- There was adequate attention and interest by all participants during the monitoring feedback

- Inadequacy of enablers package in the sub districts

- No sputum containers in some of the facilities

The team however, used the opportunity to address some the issues identified during the monitoring exercise.

The cases detection in the district still not encouraging, therefore, new strategies would be adopted to increase the case detection rate in particularly for contact tracing. The district was able to detect only 33% of its TB cases during the year under review.  Lack of fund was the major challenge faced by the programme during the year.

#### 2.3.11: Expanded Programme on Immunization (EPI)

##### 2.3.11.1: Routine Vaccination Activities

The National EPI Policy in Ghana is that each child should receive one dose of BCG at birth, three doses of PENTA (at 6, 10 and 14 weeks), four doses of OPV (at birth, 6, 10 and 14 weeks) two doses of Rota (6 and 10 weeks), one dose of IPV (at 14 weeks), two doses of measles (at 9 and 18 months ), one dose of Men. A and one dose of yellow fever. Immunization is considered one of the most cost-effective public health interventions for reducing child morbidity, mortality and disability.

Routine immunization which is ongoing in all CHPS zones was conducted at outreach and static centres in the district in the midst of the Novel Coronavirus. The wearing of nose mask, social distancing as well as hygiene etiquettes were enforced during the vaccination sessions.

The district disease control unit also organized EPI mop-up activities to trace immunization drop-outs, missed opportunities and unimmunized children.

#### 2.3.12: Neglected Tropical Diseases (NTDs) control

Onchocerciasis (river blindness), Lymphatic Filariasis, Schistosomiasis, soil transmitted helminthiasis and genital schistosomiasis are devastating, debilitating Stigmatizing and incapacitating parasitic disease that are endemic in the tropics. These diseases can be effectively controlled as a public health problem by mass drug administration.

During the last quarter of the year, the district organized training for fifteen (15) health professionals to identify, suspect, diagnosis, manage and report cases of the five tropical diseases.

#### 2.3.13: Implementation of Maternal Neonatal and Child health Nutrition Project (MCHNP)

The district received quarterly financial support from World Bank through the ministry of health and Ghana Health Service to strengthening routine community-based health services. The project covered child welfare clinic, home visit, and community durbar and community health management committee meetings at the community level and supportive supervision at the district and subdistrict levels.

In the year under review, the district received two tranches of MCHNP funds. The third and fourth quarter tranches were not received. This affected the implementation of planned activities under the project. The CHPS zones were unable to organized most of the community durbars due to the imposition of social gathering restriction in the country in year under review. In view of this funds allocated for community durbars were channelled into the purchase of weighting scales and motorbike by the Community Health Nurses. These items were clearly in dire need by the district. The district recorded 1,113 weighting sessions (both static and outreach) and weighed 56,328 children under five years. The district also conducted 1885 home visits in the year under review. Below table shows performance by subdistricts.

Table 2.7: MCHNP activities 2020

| Subdistrict | Weighing sessions | Total weighed | Home visits | CHMC meetings | Durbars organised | Supervision organised |
| --- | --- | --- | --- | --- | --- | --- |
| Ataase | 762 | 30,263 | 582 | 32 | 0 | 2 |
| Akutreso | 266 | 11,203 | 456 | 10 | 0 | 2 |
| New Edu | 325 | 14,862 | 847 | 18 | 0 | 2 |
| District | 1,113 | 56,328 | 1,885 | 60 | 0 | 6 |

# CHAPTER THREE

## KEY PERFORMANCE INDICATORS

### 3.1: Maternal Health

#### 3.1.1: Antenatal Care (ANC)

Global evidence suggests a strong correlation between benefiting from antenatal care (ANC) services and positive pregnancy outcomes. Essential interventions in ANC include intermittent preventive treatment for malaria during pregnancy (IPTp), identification and management of obstetric complications such as pre-eclampsia, tetanus toxoid immunization, intermittent and identification and management of infections including HIV. In addition, ANC affords the opportunity to promote the utilization of skilled attendance during delivery and healthy actions such as breastfeeding, early postnatal care, and family planning.

Figure 3.1: ANC Registrants, 2017-2019

|  | Percentage ANC Registrants |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 27.2 | 34.3 | 34.9 | 37.7 |
| Ataase | 58.7 | 51 | 52.4 | 62.5 |
| New Edubiase | 79.5 | 79.9 | 74.4 | 65.7 |
| Adansi South | 61.6 | 59.8 | 58.2 | 58.4 |

ANC registrants for the past three years in the district have been stagnating. This may be partly due to increase in family planning acceptors in the district. Secondly, access to ANC services is limited to clients in New Edubiase subdistrict as the only facility available is the district hospital. However, there was a significant improvement from the Ataase and Akutreso sub districts over the previous year. Outreach ANC services may help to improve attendance in New Edubiase subdistrict.

Figure 3.2: Mothers making 4th visit, 2017-2019

|  | Percentage of ANC registrants making 4th ANC visit |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 56.1 | 63.3 | 122.2 | 137.8 |
| Ataase | 64.8 | 68.3 | 80.1 | 63.1 |
| New Edubiase | 85.8 | 71.3 | 74.4 | 98.0 |
| Adansi South | 75 | 69.4 | 81.5 | 86.6 |

The district improved over the previous years, however, there were data issues with Akutreso sub district as they over recorded the mother who made the 4th visit.

Table 3.3: Average number of ANC visits per client

|  | Average number of ANC visits per client |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 2.8 | 3 | 3.4 |  |
| Ataase | 4 | 3.8 | 4 |  |
| New Edubiase | 5.1 | 5.2 | 5.6 |  |
| Adansi South | 4.4 | 4.5 | 4.7 |  |

Comparatively, the district saw a stagnation in 2018 and 2019. However, this is a good sign because pregnant women make more ANC visits before delivering.

#### 3.1.2: Prevention of Maternal and Neonatal Tetanus

Provision of at least 2 doses of tetanus-diphtheria (TD2) to pregnant women in high-risk areas is one of the key strategies for achieving elimination of maternal and neonatal Tetanus recommended by WHO/UNICEF/UNFPA. Although the Ghana is among several countries which have successfully eliminated maternal and neonatal tetanus, data collated for this shows a decline in the coverage of Tetanus vaccination among ANC clients and the Women-in-Fertile Age (WIFA) population in the district.

Poor record keeping for TD vaccination leading to incomplete data on immunization status of pregnant women is among the key factors contributing to the record of low coverage. Table below shows the trend for the past four years.

Table 3.4: TD2+ coverage

|  | Proportion of expected pregnant women receiving TD2+ |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 17.0 | 32.9 | 56.1 | 26.9 |
| Ataase | 97.2 | 78.0 | 45.4 | 60.5 |
| New Edubiase | 47.4 | 44.6 | 54.7 | 36.6 |
| Adansi South | 63.5 | 56.9 | 51.0 | 45.2 |

Comparatively, pregnant women receiving TD2+ consistently reduced over the four-year period. However, Ataase sub district improved over the previous year.

3.1.3: ANC registrants in 3rd trimester

Table 3.5: Percentage of ANC registrants in 3rd trimester

|  | Percentage of ANC registrants in 3rd trimester |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 18.1 | 20.8 | 22.6 | 18.5 |
| Ataase | 15.4 | 18.4 | 13.1 | 12.8 |
| New Edubiase | 9.1 | 8.5 | 4.6 | 4.7 |
| Adansi South | 12.4 | 13.4 | 9.7 | 9.8 |

There was stagnation in clients registering late in the district. However, pregnant women at still have the cultural belief of hiding pregnancies for a period of time before registering in most health facilities, whiles majorities of clients’ lack of access (distance) to the health facilities coupled with financial constraints.

Consistent education on importance of early registration and outreach ANC will help will help to curtail the challenge.

3.1.4: Teenage pregnancy among ANC Registrants

Table 3.6: Percentage of Teenage Pregnancies among ANC registrants

|  | Percentage of Teenage Pregnancies among ANC registrants |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 24.1 | 18.8 | 19.1 | 20.2 |
| Ataase | 20.8 | 24 | 20.1 | 20.3 |
| New Edubiase | 15.4 | 18.6 | 16.2 | 16.2 |
| Adansi South | 18.2 | 20.6 | 18.0 | 18.5 |

In 2019 the district was able to break the chain of non-performance in adolescent pregnancies due to the numerous adolescent health programmes embarked during the year. Unfortunately, COVID-19 restrictions in the year under review brought about limited adolescent programmes. Hence, the increased in teenage pregnancies in the district.

The district has to intensify its education on adolescent pregnancies using all other virtual means to bring the situation under control.

3.1.5: Antenatal registrants with parity of 5+

Table 3.7: Percentage of antenatal registrants with parity of 5+

|  | Percentage of antenatal registrants with parity of 5+ |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 8.8 | 23.1 | 22.6 | 17.3 |
| Ataase | 14.8 | 11.3 | 10.6 | 11.9 |
| New Edubiase | 11.4 | 9.4 | 7.2 | 9.5 |
| Adansi South | 12.6 | 11.4 | 10.1 | 11.4 |

Again, district saw a gradual upwards trend for parity 5+ even though family planning acceptor rate has gone up in all facilities. This is not encouraging for districts due to the obstetric complications connected with such clients.

Intensify Community sensitization on the risk associated with grand multiparity in all communities.

#### 3.1.6: Haemoglobin tested at Antenatal Care Registration and at term

One of the strategies to reduce Anaemia, is through the use of supplements to improve the health and wellbeing of the pregnant woman as well as pregnancy outcomes. One measures of the state of health of all pregnant women is to have their haemoglobin levels determined at least on their first visit for antenatal care and again when they turn 36 weeks. Anaemia in pregnant women is a risk factor for low birth weight and haemorrhage during and after delivery, which increases the risk of maternal mortality. In Ghana, the major strategy to prevent Anaemia in pregnancy is the provision of iron and folic acid (IFA) supplements during pregnancy till 6 weeks postpartum. Girls Iron and Folic Acid Supplementation (GIFT) program started in this year for adolescents in second cycle institutions and out-off school.

Table 3.8: Percentage of clients anaemic at registration (Hb< 11g/dl)

|  | Percentage of clients anaemic at registration (Hb< 11g/dl) |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 41.5 | 63.8 | 50.4 | 23.3 |
| Ataase | 37.1 | 38.2 | 24.4 | 21.4 |
| New Edubiase | 41.7 | 70.6 | 43.6 | 25.2 |
| Adansi South | 39.8 | 58.1 | 36.9 | 23.3 |

Anaemia among ANC registrants declined sharply, from 2018 rate in the year under review. This may be largely due to the introduction of GIFT program in the district. Continual distribution may help to maintain the gains made.

Table 3.9: Percentage of clients anaemic at 36wks (Hb <11g/dl)

|  | Percentage of clients anaemic at 36wks (Hb <11g/dl) |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 51.1 | 75.5 | 76.7 | 17.6 |
| Ataase | 36.5 | 43.2 | 49.4 | 29.8 |
| New Edubiase | 46.5 | 55.1 | 13.1 | 12 |
| Adansi South | 42.8 | 53.3 | 29.6 | 17.4 |

Similarly, anaemia among pregnant women at term, (36weeks) decreased considerably following the intake of iron folate during ANC attendance as a result of the introduction of pregnancy school at district and increase in ANC attendance in other facilities.

#### 3.1.7: Intermittent Preventive Treatment for pregnancy (IPTp)

Comparatively, there was consistent upwards trend in IPT1 in the district. Similarly, other doses improved from the previous years. Perhaps the improvement may be due to the number of ANC visits per client.

Table 3.10: Percentage of Pregnant women taking IPTp1

|  | Percentage of Pregnant women taking IPTp1 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 75.4 | 88.7 | 110.9 | 164.7 |
| Ataase | 50.2 | 64.7 | 58.6 | 48.8 |
| New Edubiase | 61.6 | 53.9 | 56.6 | 61.1 |
| Adansi South | 58.0 | 61.3 | 62.9 | 66.8 |

Table 3.11: Percentage of Pregnant women taking IPT2

|  | Percentage of Pregnant women taking IPT2 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 59.1 | 59.3 | 75.7 | 96.4 |
| Ataase | 42.2 | 47 | 45.2 | 35.1 |
| New Edubiase | 46 | 40 | 45 | 46.8 |
| Adansi South | 45.5 | 44.4 | 48.2 | 46.9 |

Table 3.12: Percentage of Pregnant women taking IPT3

|  | Percentage of Pregnant women taking IPT3 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 38 | 33 | 58.3 | 53 |
| Ataase | 25.8 | 28.9 | 27.4 | 23.8 |
| New Edubiase | 29.9 | 22.4 | 32.9 | 37.7 |
| Adansi South | 28.9 | 25.8 | 33.4 | 33.1 |

Table 3.13: Percentage of Pregnant women taking IPT4

|  | Percentage of Pregnant women taking IPT4 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 22.8 | 20.4 | 32.2 | 26.9 |
| Ataase | 15.3 | 14.8 | 11.9 | 10.5 |
| New Edubiase | 16 | 11.8 | 19.5 | 23.6 |
| Adansi South | 16.3 | 13.8 | 17.9 | 18.1 |

Table 3.14: Percentage of Pregnant women taking IPT5

|  | Percentage of Pregnant women taking IPT5 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 4.7 | 5.9 | 18.3 | 14.5 |
| Ataase | 9.8 | 9.6 | 5.1 | 6.1 |
| New Edubiase | 9.1 | 6.5 | 6.7 | 11.3 |
| Adansi South | 9.1 | 7.5 | 7.3 | 9.3 |

Table 3.15: IPTp1-IPTp3 Dropout rate

|  | IPTp1-IPTp3 Dropout rate |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 49.6 | 62.8 | 47.5 | 67.8 |
| Ataase | 48.6 | 55.3 | 53.3 | 51.2 |
| New Edubiase | 51.4 | 58.5 | 41.8 | 38.2 |
| Adansi South | 50.2 | 57.9 | 46.9 | 50.4 |

More than half of the pregnant women who took first dose of Sulphurdoxine Paramethamine (SP) could not take the third dose. Even though there was an improvement in almost all the five doses of SP, at the three sub districts, the dropout rates are still a concern.

Late ANC registration, failure to attend ANC sessions at appointed dates and failure to trace defaulters to take IPTp as scheduled were some of the reasons accounted for the decline.

Education on importance of IPTp intake, effective defaulter tracing of pregnant women and administration of SP tablets to pregnant women during home visits will go a long way to improve coverage.

#### Skilled Delivery

#### Institutional delivery

Globally consensus has been reached over the past years on the interventions that are significant in reducing maternal mortality. Attendance by skilled health staff during delivery is proposed to be one of the important factors and this is reflected in the use of proportion of birth attendance by skilled health staff as a benchmark indicator for monitoring progress towards the Millennium

Development Goals (MDGs). In general, births with skilled attendants are associated with lower rates of maternal mortality.

Figure 3.16: Total Institutional delivery, 2016-2018

|  | Percentage skilled deliveries |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 6.8 | 14.1 | 24.9 | 23.5 |
| Ataase | 26.8 | 24.5 | 25.7 | 22.9 |
| New Edubiase | 56.6 | 51 | 59.2 | 63.8 |
| Adansi South | 35.4 | 33.4 | 39.0 | 39.4 |

The district stagnated as compared to the previous skilled deliveries coverage. This stagnation was as a result of Ataase declining under the year of review. Activities of TBAs are prominent in Ataase subdistrict. Relevant stakeholders must put in efforts to curtail this problem.

Maternal waiting homes in the health facilities may help alleviate pregnant women’s concerns.

Table 3.17: Percentage of adolescents having skilled delivery 10-19

|  | Percentage of adolescents having skilled delivery 10-19 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 25.6 | 22.8 | 19.5 | 20.8 |
| Ataase | 21.8 | 24 | 20.3 | 19.3 |
| New Edubiase | 18.4 | 17.7 | 18.3 | 15.6 |
| Adansi South | 19.8 | 20.1 | 19.0 | 17.1 |

Both Akutreso and Ataase plateaued in deliveries offered to adolescents aged 10-19 years, whereas the district hospital declined compared to the previous year.

#### Caesarean Section Rate

The proportion of deliveries by caesarean section recorded for 2020 was above the recommended rate of between 5% and 15% of all births by the World Health Organization (WHO). This was as a result of obstetric complications coupled with devastated conditions of some cases referred from neighboring districts. Moreover, expectant mothers these days prefer caesarian section mode of delivery than spontaneous vaginal delivery due to intense pain associated with vaginal delivery.

Figure 3.18: Trend in Caesarean Section Rate, 2017 – 2020

|  | Percentage of deliveries by C section |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 0 | 0 | 0 | 0 |
| Ataase | 0 | 0 | 0 | 0 |
| New Edubiase | 19.8 | 15.5 | 19.3 | 30.0 |
| Adansi South | 13.2 | 9.5 | 11.8 | 19.7 |

#### Institutional Maternal Deaths

In 2020, a total of two (2) women died from pregnancy related causes, which increased from one death in 2019.  One of these cases was referred from Adansi Asokwa district. All the two maternal deaths were successfully audited. The audited reports concluded the cause of death as being Cerebral Oedema, and Haemorrhagic shock. Efforts will be made to prevent further occurrences in the ensuing year.

Table 3.19: Total maternal deaths

|  | Total maternal deaths |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 0 | 0 | 0 | 0 |
| Ataase | 0 | 0 | 0 | 0 |
| New Edubiase | 1 | 2 | 1 | 2 |
| Adansi South | 1 | 2 | 1 | 2 |

##### Maternal Mortality Ratio (MMR)

The two (2) maternal deaths recorded for the year reflect a corresponding increase in maternal mortality ratio, which had declined from 159/100, 000 livebirths in 2018 to 66/100,000 livebirths in 2019. The district recorded maternal mortality ratio of 127.60 per 100,000 live births in the year under review. This was slight above the national target of 125 maternal deaths per 100,000 live births.

Table 3.20: Institutional Maternal Mortality Ratio

|  | Institutional Maternal Mortality Ratio |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 0 | 0 | 0 | 0 |
| Ataase | 0 | 0 | 0 | 0 |
| New Edubiase | 121.2 | 259.7 | 108.7 | 195.7 |
| Adansi South | 79.7 | 159.0 | 66.0 | 127.60 |

##### Still Birth Rate

Stillbirths are a reflection of the quality of care given to women and newborns during antenatal and delivery. In 2018, still birth rate was 9.4% but was increased to 12.4% in 2019. It was then jumped to 16% in 2020. Most off these cases were referred from neighboring district in very bad state.

With the rollout of the perinatal death audits programme, the underlying causes of still births were identified and interventions put in place to reduce them.

Table 3.21: Percentage still births

|  | Percentage still births |  |  |
| --- | --- | --- | --- |
|  | 2018 | 2019 | 200 |
| Akutreso | 0.0 | 0.0 | 0.0 |
| Ataase | 0.0 | 2.3 | 2.6 |
| New Edubiase | 15.3 | 19.2 | 23.9 |
| Adansi South | 9.4 | 12.4 | 16.3 |

Table 3.22: Percentage of fresh still births

|  | Percentage of fresh still births |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 0.0 | 0.0 | 0.0 |  |
| Ataase |  |  | 100 | 100 |
| New Edubiase | 39.4 | 25 | 44.4 | 60 |
| Adansi South | 39.4 | 25 | 47.4 | 61.5 |

Little above sixty percent (60%) of the stillbirths were fresh stillbirths. This coverage was a leap from the 2019 figure of 47%. Improper management of labour by some Midwives coupled with herbal enema used by women in labour caused the rise.

##### Institutional Neonatal Deaths

The majority of the deaths that occurred in the neonatal period were as a result of Fetal Macrosomia, Birth Asphyxia, Hypothermia, Placenta Abruptio, Cord Prolapse and Anaemia. Interventions to reduce these conditions are clearly outlined in the National Newborn Strategy and Action plan. Perinatal death audits can unearth some of the reasons behind these deaths. From 2018, no neonatal death had occurred in Akuterso sub districts. This is remarkable because it is the most deprived sub-districts in terms of maternal, neonatal and child health services in the district. The district reported consistent decrease in neonatal deaths per 1,000 live births.

Table 3.23: Neonatal deaths per 1,00 live births

| Subdistrict | 2018 | 2019 | 2020 |
| --- | --- | --- | --- |
| Akutreso | 0.0 | 0.0 | 0.0 |
| Ataase | 7.5 | 0.0 | 0.0 |
| New Edubiase | 5.2 | 4.3 | 2.0 |
| District | 5.6 | 2.6 | 1.3 |

##### 2.3.4: Exclusive Breastfeeding at Discharge

The percentage of mother/infant pair exclusively breastfeeding at discharge has seen a consistent increase since 2018. This gain should be sustained through scaling up the baby friendly initiative in all health facilities providing maternity services. Mothers should be supported to sustain the practice of exclusive breastfeeding when they go back to their communities. However, some facilities still have challenge in recording this indictor a seen in over 100%  in Ataase and New Edubiase subdistricts.

Table 3.24: Percentage of Mother/Infant pairs Exclusively Breastfeeding at Discharge, 2017 - 2020

|  | 2017 | 2018 | 2019 | 2020 |
| --- | --- | --- | --- | --- |
| Akutreso | 100 | 100 | 100.0 | 100.0 |
| Ataase | 78.5 | 88.6 | 100.0 | 102.8 |
| New Edubiase | 94.1 | 100 | 99.9 | 100.3 |
| District | 94.52 | 92.32 | 99.9 | 100.9 |

#### Postnatal care

##### Postnatal registrants

Table 3.25: Postnatal Coverage

|  | Postnatal Coverage |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 13.4 | 18.8 | 25.2 | 24.2 |
| Ataase | 31.7 | 33.4 | 32.8 | 24.5 |
| New Edubiase | 75.3 | 56.3 | 62.6 | 66.9 |
| Adansi South | 46.1 | 40.1 | 43.4 | 41.4 |

The district recorded a decline in its postnatal care coverage from previous year. This decrease from 43.4.1% in 2019 to 41.4% was largely noticed in Ataase sub-districts.  The issue has to do with mothers who delivered with Traditional birth Attendants (TBA) and homes. Majority of them do not attend Postnatal Clinic especially when there were no complications after the delivery. We will intensify monitoring with known TBAs so to increase coverage in the coming

PNC registrants seen within the first 48 hours after delivery

Table 3.26: Percentage of PNC registrants seen within the first 48 hours after delivery

|  | Percentage of PNC registrants seen within the first 48 hours after delivery |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 57.1 | 76 | 95.8 | 95.1 |
| Ataase | 66.4 | 73.3 | 77.1 | 81.5 |
| New Edubiase | 82.7 | 91.9 | 95.1 | 100.0 |
| Adansi South | 76.7 | 84 | 89.4 | 95.0 |

Under normal circumstance, all postpartum mothers and their babies must have their first postnatal services within the first two days after delivery. In 2019, more than 90% of all post-partum mothers had their postnatal care on day 1 or 2 after delivery. Even though this was improvement over the previous years, yet the district must strengthen this indicator.

### 3.2: Adolescent Health Services

The National Adolescent Health and Development Programme constitute a comprehensive care for young people (10-19yrs). This comprehensive care is about bridging the gap between clinical and public health programmes to promote adolescent health. The elements of this comprehensive care are promotive, preventive, clinical and rehabilitative health care.

The goal of the ADHD Programme is to integrate adolescent friendly health services into both public and private health facilities at all levels of service delivery including the community level. The key strategy of the Programme is to make health services adolescent/youth friendly. This means health services at every level should be available, accessible, acceptable, equitable and affordable for every young client no matter their social or economic status. The ADHD programme targets primarily young people aged 10-19years), parents, teachers, social workers and health workers (the stakeholders) and health and related sectors (the system). The introduction of Adolescent Safety net program in the district had increased the attendance of most adolescent services.

The proportion of adolescents who sought antenatal care services for 2020 increased marginally from 18% in 2019 to 18.8%. Coupled with this was a decrease in the proportion of adolescents accessing family planning services. However, proportions of adolescents accessing safe abortion services increased indicating that most adolescent indulge in sex without protection.

##### 3.2.1: Adolescent Pregnancies

Adolescent pregnancy presents both health and social implications. Adolescents who get pregnant are more constrained in their ability to pursue educational opportunities than their counterparts who delay childbearing. Adolescent pregnancy contributes to the cycle of maternal mortality and morbidity because adolescent mothers are more likely to experience adverse pregnancy outcomes than their older counterparts. In addition, babies born to adolescent mothers are at increased risk of sickness and death; therefore, adolescents need special attention during pregnancy.

Figure 3.27: Trend in Percentage of Adolescents (10-19 years) attending ANC 2018-2019

|  | Adolescent pregnancy |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 22.8 | 17.6 | 19.1 | 20.1 |
| Ataase | 19.5 | 23.9 | 20.1 | 21 |
| New Edubiase | 15.4 | 18.6 | 16.2 | 16.2 |
| Adansi South | 17.7 | 20.5 | 18.0 | 18.8 |

There was slight increase in adolescent pregnancies which was largely seen in Akutreso and Ataase subdistricts.  The drop seen in New Edubiase may be attributed to the number of awareness creations on adolescent health and sexuality embarked by the family health unit of the directorate in 2019.

3.2.2: Adolescent Delivery

Table 3.28: Adolescent delivery

|  | Adolescent skilled delivery |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 25.6 | 22.8 | 19.5 | 20.8 |
| Ataase | 21.8 | 24.0 | 20.3 | 19.3 |
| New Edubiase | 18.4 | 17.7 | 18.3 | 15.6 |
| Adansi South | 19.8 | 20.1 | 19.0 | 17.1 |

Skilled delivery by adolescents saw a decrease as few teenagers delivered in the health facilities compared to 2019. Stigmatization of teenagers at maternity units may have contributed to low patronage by the adolescent. Training on customer care in maternity units may help to reduce the manners.

3.2.3: Adolescent Abortion

Table 3.29: Adolescent Abortion

|  | Adolescent Abortion |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 0.0 | 0.0 | 0.0 | 0 |
| Ataase | 26.2 | 25.5 | 36.4 | 15.4 |
| New Edubiase | 17.6 | 21.1 | 20.7 | 23 |
| Adansi South | 22.5 | 22.9 | 27.8 | 20.8 |

Little above 20% of the pregnant girls medically terminated their pregnancies with the aim of either continue their education, apprenticeship or vocation. It is expected that more adolescent girls will enrol in family planning services rather than indulge in abortions

3.2.4: Adolescent Family Planning

Table 3.30: Adolescent family planning

|  | Adolescent family planning |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 2.2 | 17.4 | 19.2 | 0.0 |
| Ataase | 22.3 | 24.6 | 21.2 | 8.3 |
| New Edubiase | 17.6 | 19.5 | 16.1 | 13.0 |
| Adansi South | 16.5 | 21.7 | 19.1 | 11.4 |

Adolescent family planning sharply decreased from its previous coverage. It decreases from 19% to 11% in 2019 and 2020 respectively. The rate in Akutreso subdistrict must investigated as it may be as a result of data error.

### 3.3: Family Planning (FP)

Pregnancy by choice and not by chance is the basic requirement for women’s health. Fertility regulation is also a major component of the safe motherhood strategy and has been delineated under the family planning programme for the purpose of emphasis and increased focus. The goal of the family planning is to assist couples and individuals of all ages achieve their reproductive goals and improve their general reproductive health. The strategies adopted include the provision of information, education and counseling, affordable contraceptive services and the prevention and management of reproductive tract infections and STIs/HIV among others. During the year under review the programme carried out various interventions, which have been reflected in its performance discussed below:

##### 3.3.1: FP Acceptor Rate

The district did not meet its annual family planning acceptor rate of 40%. However, it improved from previous rate. Akutreso and Ataase subdistricts contributed to non-achievement of the district target. This may be attributed to the failure in re-registration of clients who were on long term methods. Monitoring of re-registration of long-term family planning methods will be intensified in the ensuing year.

Table 3.31: Family Planning Acceptor rate

|  | Family Planning Acceptor rate |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 16.4 | 18.8 | 41.1 | 33.0 |
| Ataase | 32 | 35.5 | 37 | 34.5 |
| New Edubiase | 22.1 | 30.9 | 21.1 | 36.2 |
| Adansi South | 25.4 | 30.8 | 31.3 | 34.9 |

Table 3.32: Proportion of New Family Planning Acceptors

|  | Total Family Planning New Acceptors |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 44.0 | 18.1 | 25.1 | 18.6 |
| Ataase | 11.2 | 23.7 | 27.5 | 19.1 |
| New Edubiase | 35.2 | 23.5 | 42.0 | 29.5 |
| Adansi South | 33.3 | 23.0 | 31.0 | 23.3 |

Even though family planning acceptor rate has increased in the year 2020, first ever family planning users declined considerably. This may be due to limited health education on family planning in the communities. The Reproductive and Child Health Unit and Health Promotion Unit must intensify health education targeting first ever users.

Table 3.33: Total Family Planning Continuing Acceptors

|  | Total Family Planning Continuing Acceptors |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 347 | 594 | 1 219 | 1088 |
| Ataase | 2 121 | 2 621 | 2 655 | 2839 |
| New Edubiase | 1 264 | 2 141 | 1 137 | 2432 |
| Adansi South | 3 732 | 5 356 | 5 011 | 6359 |

Failure to re-register continuous users of long term and permanent family planning methods was the cause of low performance in coverage experienced by New Edubiase sub district

Akutreso sub district did remarkably well in re-registering their long term and permanent continuous users. All efforts should be geared towards re-registration of continuing acceptors to increase coverage.

Table 3.34: Total family planning visits

|  | Total family planning visits |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 2 826 | 749 | 1 143 | 749 |
| Ataase | 3 155 | 3 690 | 2 947 | 3690 |
| New Edubiase | 2 668 | 2 828 | 1 486 | 2828 |
| Adansi South | 8 649 | 7 267 | 5 576 | 7267 |

The total visits for New Edubiase and Ataase were not encouraging and must be intensified in the coming years

##### Couple Year Protection (CYP)

The CYP measures the programme performance by providing information about the volume of all contraceptives sold or distributed and it’s an immediate indication of the volume of programme activity in line with programme plans, projections and expectations, the district CYP trend showed significant improvement over the years. This trend can be attributed to the scale-up of task shifting allowing community health nurses to provide implant services, an overall increased access to long acting and reversible methods and improved commodity security.

Table 3.35: Total couple year protection

|  | Total couple year protection |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 598.9 | 537.1 | 1 126.3 | 559.6 |
| Ataase | 3 536.3 | 1 866.4 | 2 750 | 1989.8 |
| New Edubiase | 1 241.6 | 1 508.7 | 1 915.8 | 1680.1 |
| Adansi South | 5 376.9 | 3 912.2 | 5 792.1 | 4229.4 |

### 3.4: Child Health

The child health programme focuses on the first five years of life as the most vulnerable period of childhood, which sets the tone for child growth and development thereafter. Although progress has been made over the years in reducing childhood morbidity and mortality, there are several challenges that need to be addressed. Using Penta, and Measles-Rubella as proxy the various subdistricts performances are compared below;

Expanded programme on Immunization

Table 3.36: BCG coverage 2017-2020

|  | BCG |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 74.1 | 67.6 | 72.1 | 85.9 |
| Ataase | 114 | 106.8 | 117.1 | 105.3 |
| New Edubiase | 132.5 | 93.7 | 81.4 | 112.4 |
| Adansi South | 114.6 | 94.9 | 95.1 | 104.8 |

BCG coverage for the year under review was more that 100% in New Edubiase and Ataase subdistricts. These are major referred facilities in the district, hence babies born to these referred mothers were given BCG before discharge back to their districts.

Table 3.37: Penta1 Coverage_2017-2020

|  | Penta 1 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 87.6 | 64.8 | 68.1 | 77.8 |
| Ataase | 118.6 | 113 | 114 | 115.5 |
| New Edubiase | 105 | 85.9 | 77.6 | 94.3 |
| Adansi South | 107.9 | 93.9 | 91.5 | 100.6 |

First dose of Penta is always high compare to Penta 2 and 3 in the district. However, Akutreso and New Edubiase subdistricts did not meet the annual target of 96%. Home visit, routine outreach and mop-up activities must be intensified in these two subdistricts.

Table 3.38: Penta 2 coverage

|  | Penta 2 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 70.3 | 61.7 | 69.6 | 81.4 |
| Ataase | 110.1 | 105.9 | 113.1 | 112.7 |
| New Edubiase | 111.6 | 81.2 | 78 | 91.2 |
| Adansi South | 103.9 | 88.4 | 91.6 | 98.7 |

Penta 2 also appreciated in the 2020 as compared to 2019. Ataase sub district one again exceeded the target of 96%. Error in data capturing among others may have contributed excess increase

Table 3.39: Penta 3 coverage, 2017-2020

|  | Penta 3 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 95.9 | 64.8 | 71.4 | 81.7 |
| Ataase | 122.6 | 114.3 | 115.7 | 111.8 |
| New Edubiase | 124.2 | 84.9 | 76.9 | 89.9 |
| Adansi South | 118.7 | 94.1 | 92.6 | 97.9 |

Penta 3 coverage saw an improvement against last year. Again, Akutreso and New Edubase subdistrict did not meet the target of 96%.

Table 3.40: Measles-Rubella 1 coverage

|  | Measles-Rubella 1 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 77.6 | 68.8 | 66.1 | 66.7 |
| Ataase | 111.5 | 96.7 | 93.6 | 91.3 |
| New Edubiase | 92.1 | 70.2 | 61 | 84.6 |
| Adansi South | 97.9 | 81.3 | 75.8 | 84.4 |

First dose of Measles-Rubella coverage was not able to meet its target. Ataase subdistrict which met the 90% target also declined from 2019 coverage. Defaulter tracing has become an issue in the district even though support for home visit is being provided. The district has to intensify monitoring on this area.

Table 3.41: Measles-Rubella 2 coverage, 2017-2020

|  | Measles-Rubella 2 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 68.7 | 41.6 | 50.2 | 53.3 |
| Ataase | 91.5 | 82.1 | 83.3 | 89.8 |
| New Edubiase | 80.8 | 59.4 | 47.1 | 79.9 |
| Adansi South | 83.3 | 66.1 | 63.1 | 79.6 |

Measles-Rubella 2 appreciated significantly in all subdistricts in the year under review. Home was intensified in this area. All effort must made to maintain this activity in coming years.

Table 3.42: MR1-MR2dropout rate

|  | MR1 to MR2 dropout rate |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 11.5 | 39.5 | 24.1 | 24.5 |
| Ataase | 18.4 | 15.4 | 11.5 | 3.4 |
| New Edubiase | 13.7 | 16.3 | 23.0 | 8.6 |
| Adansi South | 15.7 | 19.2 | 17.1 | 8.4 |

Measles-Rubella1 to Measles-Rubella 2 dropout rate was within the annual target of 10%. Intensified home visits, among other were some of the activities implemented in this area.

Table 3.43: LLIN given to Children

|  | Proportion of MR2 children given LLINs |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 86 | 100 | 94 | 95 |
| Ataase | 77 | 87 | 89 | 96 |
| New Edubiase | 52 | 92 | 88 | 96 |
| Adansi South | 69 | 90 | 90 | 96 |

The proportion of children 18-59 months due for Measles-Rubella 2 antigen given Long-Lasting Insecticide Nets improved in all subdistricts and resulted in exceeding the district target of 80%   in the year under review. Almost all children who received Measles Rubella 2 Antigen at various Child Welfare Clinic were given Mosquito nets in the district.

### 3.5: Nutrition

The Maternal, Infant and Young Child Nutrition Programme, Nutrition Rehabilitation with emphasis on management of severe acute malnutrition and moderate malnutrition, Micronutrient Deficiency Control and Nutrition Support for Vulnerable Groups were all implemented.

In the year under review, priority actions were focused on Maternal, Infant and Young Child

Nutrition (MIYCN), Improving coverage of Vitamin A Supplementation for children 6- 59 months and Integration of management of severe acute malnutrition protocols into Integrated

Management of Neonatal and Childhood Illnesses.

##### Maternal, Infant and Young Child Nutrition

National recommendations on breastfeeding stipulates that all infants be put to the breast within 30 minutes after delivery and be placed in skin-to-skin contact for at least 1 hour. Early initiation of breastfeeding has been shown to reduce neonatal deaths by about 13%; early initiation of breastfeeding has been routinely monitored over the years as an indicator of quality of care for all facilities offering maternity services. For sometime now, feeding status of babies at 3 and 6 months have been included in the routine health data systems to be monitored.

The National Nutrition Policy and New-born Strategy has targeted that at least 85% of all newborns should be put to the breast within 30 minutes of delivery. Routine data analyses show that nearly 99.9% infants delivered in health facilities are put to breast within the first 30 minutes of life, which may be indicative of the fact that the targets have been achieved in the district. (refer to table 3.9 above)

##### Exclusive Breastfeeding at 3 Months

In 2016, a new indicator was introduced into the routine data collection system to track how infants are fed at the time of PENTA 3 vaccination, when the babies are about 3months.

Figure 3.44: Exclusive Breastfeeding at 3 Months, 2018-2019

| Subdistrict | 2018 | 2019 | 2020 |
| --- | --- | --- | --- |
| Akutreso |  | 62.6 | 79 |
| Ataase |  | 100.1 | 76.1 |
| New Edubiase |  | 89.3 | 88.9 |
| District |  | 91.5 | 80.9 |

Figure above shows the percentage of infants who were being exclusively breastfed at 3 months in 2018 to 2020. Caregivers who presented their infants at 3 months for growth monitoring and promotion were asked how the infants were fed. The responses were coded under whether they were giving only breast milk or they were adding other liquids or foods. About 80% of the caregivers indicated that they were giving only breast milk at the time of the visit. Frontline health workers were trained in breastfeeding promotion, with the aim of designating more facilities as baby friendly. This effort contributed to the massive promotion of exclusive breastfeeding in the district in the year 2019. However, there was almost a decline of 10% in 2020 with the exception of Akutreso subdistrict which improved massively.

#### Growth Monitoring and Promotion

Growth monitoring and promotion services are provided through static points and outreach activities to monitor the growth of children. The weights of children are monitored monthly with the aim of detecting onset of under nutrition early and intervening to prevent growth faltering.

All children 0-59 months who attend growth-monitoring sessions are weighed and the weight plotted on the growth chart to determine their growth trend. Monthly data on nutrition status of all children weighed are recorded.

Table 3.45: Child Welfare Clinics, 0-11 months, 2017-2019

|  | CWC coverage, 0-11 month |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 44.8 | 51.9 | 52.7 | 60.8 |
| Ataase | 83.8 | 93.1 | 79.4 | 76.5 |
| New Edubiase | 113.4 | 99.4 | 73.2 | 103.3 |
| Adansi South | 89.0 | 88.6 | 72.4 | 84.6 |

The district recorded 84.6% coverage for children 0-11 months during child welfare clinic. This was an increase from the previous year.

Table 3.46: CWC Coverage, 12-23 months

|  | CWC coverage, 12-23 months |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 84.2 | 56.3 | 46.5 | 41.7 |
| Ataase | 55.7 | 86.2 | 45.7 | 61.2 |
| New Edubiase | 95.6 | 93 | 50.1 | 67.4 |
| Adansi South | 76.6 | 83.8 | 47.6 | 60.4 |

As the ages of the children progress, attendance to child welfare clinic retrogress. This is because most children at age two start schooling especially at the urban areas. This is clearly seen at age bracket 12-59 months. The district recorded over 60% and 11.8% coverage for 12-23 months and 24-59 months at child welfare clinic respectively in 2020.

Table 3.47: CWC Coverage 24-59 months

|  | CWC coverage, 24-59months |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 13.1 | 13.1 | 14.3 | 10.1 |
| Ataase | 14.9 | 13 | 5.4 | 11.5 |
| New Edubiase | 21.9 | 23.3 | 8.5 | 12.9 |
| Adansi South | 17.4 | 17.2 | 8.1 | 11.8 |

Cumulatively the district scored 26% child welfare clinic coverage for children under five years in 2019 as compared to 32% in 2020. Adequate school health services in Ataase and New Edubiase subdistricts largely contributed to the increase in the coverage.

Table 3.48: CWC Coverage, 0-59 months

|  | CWC coverage, 0-59 months |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 27.1 | 24.8 | 24.2 | 23.4 |
| Ataase | 32.4 | 37.8 | 25.8 | 30.1 |
| New Edubiase | 47.4 | 44.7 | 26.5 | 37.3 |
| Adansi South | 37.5 | 38.3 | 25.8 | 31.8 |

### 3.6: Clinical Care Services

##### OPD Attendance

The district was unable to achieve its OPD per capita of 1 in the year 2020. All the subdistricts declined in 2020 compared to the previous year with the exception of Ataase  which improved from its previous year.

Table 3.49: OPD per capita, 2017-2019.

|  | OPD per Capita |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso | 0.10 | 0.12 | 0.22 | 0.18 |
| Ataase | 0.27 | 0.30 | 0.24 | 0.26 |
| New Edubiase | 1.00 | 1.00 | 1.00 | 0.79 |
| Adansi South | 0.55 | 0.56 | 0.56 | 0.46 |

The percentage of clients insured under National Health Insurance Scheme at the OPD has declined significantly over the past year from 83% in 2019 to 78% in 2020. This indicated that almost 80% of OPD attendance depend on the health insurance scheme; therefore, delay in the re-imbursement has a heavy toll on the management of health facilities.

Table 3.50: OPD Insured clients, 2017-2019

|  | OPD NHIS Insured Client |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | 2020 |
| Akutreso |  | 77 | 77.1 | 69.5 |
| Ataase |  | 81.3 | 81 | 75.2 |
| New Edubiase |  | 85.8 | 84.1 | 80.2 |
| Adansi South |  | 84.4 | 83 | 78.2 |

Figure 3.1: Top twenty diseases seen at the OPD, 2019

The top ten diseases reported for the year under review showed Malaria as leading, followed by Upper Respiratory Tract Infections, Anaemia, Pneumonia Diarrhoea, with the last being other nutrition disorders.

##### Admissions and Institutional Deaths

Total Admissions for the period under review was 3,353 compared to 39,282 in 2018. Out of this 80.1% were NHIS active card holders compared to 78.4% in 2018.

The total institutional deaths for the reporting period were 29 compared to 40 in 2018 given an all-cause mortality rate of 8.6 per 1000 admission compared 10.5 per 1000 admissions in the previous year.

Table 3.51 : Summary of Hospitals admissions and outcomes 2019

|  | INSURED PATIENTS |  |  |  | NON-INSURED PATIENTS |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ADMISSION |  | DEATH |  | ADMISSION |  | DEATH |  |
|  | M | F | M | F | M | F | M | F |
| 0-28 days | 65 | 68 | 0 | 0 | 0 | 1 | 0 | 0 |
| 1-11 months | 74 | 65 | 0 | 0 | 15 | 10 | 0 | 0 |
| 1 – 4 Years | 232 | 171 | 0 | 0 | 40 | 38 | 0 | 0 |
| 5 – 9 Years | 58 | 54 | 0 | 0 | 21 | 24 | 0 | 0 |
| 10 – 14 Years | 20 | 28 | 1 | 0 | 12 | 11 | 1 | 0 |
| 15 – 17 Years | 21 | 119 | 0 | 0 | 6 | 19 | 0 | 0 |
| 18 – 19 Years | 15 | 131 | 0 | 0 | 10 | 26 | 0 | 0 |
| 20 – 34 Years | 54 | 912 | 0 | 0 | 55 | 112 | 4 | 2 |
| 35 – 49 Years | 44 | 269 | 0 | 0 | 53 | 60 | 2 | 2 |
| 50 – 59 Years | 29 | 54 | 3 | 2 | 32 | 27 | 1 | 0 |
| 60 – 69 Years | 35 | 52 | 1 | 1 | 21 | 16 | 0 | 0 |
| 70 Yrs & Above | 40 | 75 | 4 | 3 | 23 | 36 | 2 | 0 |
| Total All Ages | 687 | 1998 | 9 | 6 | 288 | 380 | 10 | 4 |

Figure 3.2: Clinical Care Performance_2014-2019

There was sharp increase in total OPD attendance for the year under review. This is good for the district especially when the it is position itself to the Universal health coverage. Total admissions and deaths also saw an improvement over the previous year.

Figure 3.3: Percentage Inpatients insured_2014-2019

Over the years, national Health Insurance scheme active clients on admission have been declining. However, following public education on the need to enroll in National Health Insurance scheme, the district improved on its insured client on admission in the year under review.

Figure 3.4: Total number of deaths_2014-2019

There has been a significant improvement in management of complicated cases in the hospital. This had resulted in decreased in institutional deaths from 73 in 2014 to 29 in 2019.

Figure 3.5: All-cause mortality rate (/1000) _2014-2019

In every 1,000-population admitted at the district hospital, about 9 of them dead in the year under review. This has been an improvement over the past years

Table 3.52: number of Malaria deaths _2014-2019

|  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Number of Patients below 5 years of Age Dying of Malaria | 1 | 0 | 0 | 0 | 2 | 0 |
| Number of Patients 5 years and above Dying of Malaria | 2 | 1 | 2 | 1 | 1 | 0 |
| Total malaria deaths | 3 | 1 | 2 | 1 | 3 | 0 |

The district recorded zero malaria death in this year under review. Strategies used included intensified distribution of long-lasting Insecticide Nets to mothers and children, increased IPT coverage for pregnant women and effective case management using ACTs in all facilities.

### 3.6: Community-Based Health Planning and Services (CHPS)

Functional CHPS compounds increased from 3 in 2018 to 4 in 2019. Ataase subdistrict has highest number of compounds with no CHPS compound in New Edubiase sub-district. Three (3) CHPS Compounds are on the various levels of completion in Bepoase, Menang and Tonkoase (Community initiated).

Table 3.53: CHPS progress by sub-districts 2019

| Sub-district | Electoral Areas | Demarcated CHPS Zones | Functional CHPS zones | CHPS Zones with Cpds | Uncompleted CHPS Cpds |
| --- | --- | --- | --- | --- | --- |
| Akutreso | 5 | 5 | 5 | 1 | 1 |
| Ataase | 16 | 16 | 16 | 3 | 1 |
| New Edubiase | 9 | 9 | 9 | 0 | 1 |
| Total | 30 | 30 | 30 | 4 | 3 |

CHPS contribution to the overall service delivery continues to improve. Fore instead in 2019, CHPS contributed 8.1% to the total ANC registrants compared to 2.1% in 2018. This improvement was as a result of increased in number of Midwifes in CHPS compounds.  There was slight decline in coverage in Family planning acceptor rate, OPD Attendance and Epi using Penta 3 as proxy.

Table 3.54: CHPS contribution to selected service delivery_ 2016-2019

|  | CHPS |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2016 | 2017 | 2018 | 2019 |
| Total OPD attendance | 6.5 | 7.0 | 8.9 | 8.1 |
| ANC registrants | 10.2 | 3.2 | 2.1 | 8.2 |
| Number of mothers, all deliveries | 0.0 | 1.1 | 2.6 | 7.8 |
| Number of PNC registrants | 0.0 | 0.8 | 1.7 | 7.8 |
| Total family planning acceptors | 41.3 | 75.9 | 57.5 | 47.4 |
| Number of children immunized by age 1 - Penta 3 | 90.4 | 91.8 | 89.0 | 81.5 |

# CHEAPTER FOUR

## CHALLENGES AND RECOMMENDED MITIGATIVES

### Challenges and Way Forward

#### 1.0 Slow pace of CHPS implementation

- Train district and sub-district staff on implementation guidelines for the new CHPS policy.

- Liaise with relevant Stakeholders to provide funds for CHPS implementation in the district.

- Advocate for District Assemblies and Community leaders to invest in CHPS Compound constructions and equip them with basic medical equipment and logistics

#### 2.0 Inadequate essential health staff and increasing applications for posting out

- Conscientizing Staff about offering selfless services

- Lobby for additional essential staff

- Advocate for District Assembly to provide sponsorship for students to retain them in the district

- Provision of incentive packages to staff who accept posting to deprived communities

#### 3.0 No GOG funding for goods and services

- Ride at the back of programme funds to support the running of the directorate

- Advocate for district hospital to support District Health Management Team

- Liaise with the District Assembly to provide financial support to the directorate

#### 4.0 Delayed reimbursement of NHIS claims submitted to NHIA by health Facilities

- Advocate for 50% percentage front-loading of claims submitted before vetting and approval processes are done.

- Assign officers to NHIS claims processing to speed up submission rate

#### 5.0 Inadequate

#### • Logistics, medicines, supplies, equipment, transport

Advocate for the provision of one extra vehicle and five motorbikes for the district

#### 6.0 Dwindling support for EPI

Advocate for procurement EPI Vaccine fridges and other logistics by the District Assembly

#### 7.0 Inadequate EMONC equipment

Advocate for supply of EMONC equipment by the District Assembly

8.0 Increasing MDR

Improve TB Case Management and TB Case management

9. High numbers of children left out of EPI

Implement Reaching Every Child (REC) Strategy

10. Weak disease surveillance and response at the sub-district level

IDSR outbreak investigations and response training

Daily records review at OPDs

## Appendix

### A: Holistic Assessment Indicators and Scores

| Indicator | Performance |  |  | Performance (P) Change and Gap to Target |  |  |  | Outcome |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 | Change | P-T Gap Analysis | Target 2019 | Assessed score |  |
| Family planning Acceptor rate | 25.40% | 30.80% | 31.30% | 1.62 | -21.75 | 40.00% | 1 |  |
| Couple Year Protection (CYP)) | 5,377 | 3,912 | 5,792 | 48.05 | -48.05 | 11,149 | 1 |  |
| Proportion of deliveries attended by trained health workers | 35.40% | 33.30% | 39.00% | 17.12 | -35 | 60.00% | 1 |  |
| Proportion of newborns receiving postnatal care (PNC) within 48 hours from birth | 76.70% | 84.00% | 89.40% | 6.43 | 11.75 | 80.00% | 2 |  |
| The proportion of children due for Measles-Rubella 2 receiving LLIN | 69.00% | 90.00% | 89.00% | -1.11 | 11.25 | 80.00% | 2 |  |
| Proportion of mothers who made at least four ANC visits | 75.00% | 69.40% | 81.50% | 17.44 | 4.49 | 78.00% | 2 |  |
| Doctor to population ratio | 1:92,059 | 1:94,224 | 1:48,395 | -48.64 | 545.27 | 1:7,500 | -2 |  |
| Nurse to population ratio |  | 0.48 | 0.44 | 8.95 | 28.89 | 0.35 | 1 |  |
| Midwife to Women in Fertility Age (WIFA) population ratio | 1:1,700 | 1:1,190 | 0.71 | 18.66 | 38.29 | 0.53 | 1 |  |
| Per capita Out Patient Department (OPD) attendance | 0.55 | 0.56 | 0.56 | 0 | -44 | 1 | 1 |  |
| Proportion of outpatient who are insured | 87.30% | 84.40% | 83.00% | -1.66 | 1.22 | 82.00% | 2 |  |
| Health facility density per 100,000 | 6 | 6 | 7 | 16.67 | -53.33 | 15 | 1 |  |
| Proportion of functional Community Health Planning and Services (CHPS) zones | 100.00% | 100.00% | 100.00% | 0 | 20 | 80.00% | 2 |  |
| Proportion of facility deaths that are medically certified | 16.70% | 100.00% | 100.00% | 0 | 25 | 80.00% | 2 |  |
| Incidence rate of diabetes (using OPD as proxy) | 0.1 | 0.2 | 0.3 | 50 | -100 | 01-May | 1 |  |
| Incidence rate of Hypertension (using OPD as proxy) | 1.3 | 1.6 | 1.1 | -31.25 | -100 | 05-Oct | -2 |  |
| Proportion of children U5 who were measured to assess stunting | 0.20% | 0.00% | 3.30% |  | -67.3 | 10.00% | 1 |  |
| Prevalence of anaemia in pregnant women at 36 weeks of gestation | 43.00% | 53.30% | 29.70% | -44.28 | 18.8 | 25.00% | 0 |  |
| Children under five years who are underweight | 3.50% | 2.30% | 1.10% | -52.17 | -63.33 | 3.00% | -2 |  |
| Institutional all-cause mortality rate per 1000 | 10.3 | 10.5 | 8.7 | -17.14 | -51.67 | 18 | 2 |  |
| Institutional Maternal Mortality Ratio per 100,000 | 79.7 | 159 | 66 | -58.49 | -47.2 | 125 | 2 |  |
| Still birth rate per 1000 | 25.6 | 9.4 | 12.4 | 31.91 | 3.33 | 12 | -2 |  |
| Percentage of maternal deaths that are audited | 100.00% | 100.00% | 100.00% | 0 | 0 | 100.00% | 2 |  |
| Adolescent mortality rate per 10,000 | 3.7 | 0.0 | 2.4 |  | -33.33 | 1.8 | -2 |  |
| Proportion of Total Mortality attributed to unsafe water, unsafe sanitation and lack of hygiene |  | 0 | 0 | 100% | -100 | 0.5 | 2 |  |
| Proportion of total mortality attributed to external causes |  |  | 3.5 |  | -99.99 | 05-Oct | 0 |  |
| Proportion of total mortality attributed to non-communicable diseases ( Neoplasm, Circulatory and cardiac conditions, Diabetes, Chronic Obstructive respiratory diseases) |  | 25 | 44.8 | -79.2 | -11.6 | 30-50 | 1 |  |
| Proportion of Hospitals (public) with mental health units | 100.00% | 100.00% | 100.00% | 0 | 0 | 100.00% | 2 |  |
| Proportion of hospitals (public) with functional emergency department | 100.00% | 100.00% | 100.00% | 0 | 0 | 100.00% | 2 |  |
| Percentage of District Hospitals with Functional Public Health Units | 100.00% | 100.00% | 100.00% | 0 | 0 | 100.00% | 2 |  |
| Data completeness for WASH/IPD reporting form |  | 100.00% | 100.00% | 0 | 42.86 | 70.00% | 2 |  |
| Proportion of planned Integrated Districts supervisory visits undertaken |  | 75.00% | 75.00% | 0 | -25 | 100.00% | 1 |  |
| Proportion of health facilities (public and private) providing data in the DHIMS2 | 100.00% | 100.00% | 100.00% | 0 | 17.65 | 85.00% | 2 |  |
| Completeness of reporting by health facilities |  | 98.50% | 96.40% | -2.13 | 0.42 | 96.00% | 2 |  |
| Hospital beds per 1000 population | 0.73 | 0.71 | 0.69 | -2.63 | -30.78 | 1 | 0 |  |
| Average length of stay at the accident and emergency (A&E) ward of the Hospital (in days) | 1.6 | 2 | 0.2 | -100 | -100 | 2 | -2 |  |
| Percentage Bed occupancy rate for the Regional Hospital | 57.70% | 47.60% | 48.10% | 1.05 | -31.29 | 70% | 1 |  |
| Average number of medicines prescribed per patient encounter (public facilities) |  | 2.9 | 3 | 3.45 | 0 | 3 | 2 |  |
| Percentage of encounters with an injection prescribed (public facilities) |  | 4.50% | 16.10% | 257.78 | -19.5 | 20.00% | 0 |  |
| Percentage of medicines prescribed by generic name (public facilities) |  | 91.10% | 93.40% | 2.52 | -6.6 | 100.00% | 1 |  |
| Percentage of prescriptions with antibiotics(public facilities) |  | 52.00% | 58.10% | 11.73 | 190.5 | 20.00% | -2 |  |
| Penta 3 coverage | 118.70% | 94.00% | 92.20% | -1.91 | -4.95 | 97.00% | 1 |  |
| Measles-Rubella 2 coverage | 83.30% | 66.10% | 62.60% | -5.3 | -30.44 | 90.00% | -1 |  |
| Proportion of pregnant women tested for syphilis | 62.40% | 75.20% | 77.70% | 3.32 | 29.5 | 60.00% | 2 |  |
| TB Case notification rate | 57.60% | 56.20% | 92.30% | 64.23 | 53.83 | 60.00% | 2 |  |
| TB treatment success rate |  | 97.10% | 72.20% | -25.64 | -19.78 | 90.00% | -2 |  |
| Tuberculosis case fatality rate |  |  | 22.20% |  | 344 | 5.00% | -2 |  |
| Proportion of suspected malaria cases that were tested for malaria before treatment | 99.20% | 99.60% | 101.70% | 2.11 | 7.05 | 95.00% | 2 |  |
| Institutional Malaria Under 5 Case Fatality Rate | 0.00% | 0.30% | 0.00% | -100 | -100 | 0.20% | 2 |  |
| Malaria mortality rate per 1000 | 0.01 | 0.03 | 0 | -100 | -100 | 1.5 | 2 |  |
| Malaria incidence rate per 1000 | 99 | 161 | 158 | -1.98 | -4.17 | 165 | 2 |  |
| Non- polio AFP rate | 2 | 1 | 7 | 600 | 250 | 2 | 2 |  |
| Surgical site infection rate | 1.20% | 0.20% | 0.00% | -100 | -100 | 5.00% | 2 |  |
| IPTp3 Coverage | 28.90% | 25.80% | 33.40% | 29.46 | -33.2 | 50.00% | 1 |  |
| Case fatality rates for epidemic prone diseases (Cholera, Meningitis, Yellow fever | 0.00% | 0.00% | 0.00% | #DIV/0! | -100 | 5.00% | 2 |  |

### B: Sector wide Indicators

EPI

| org | BCG - Children Vaccinated 2017 | BCG - Children Vaccinated 2018 | BCG - Children Vaccinated 201 | OPV/Polio 1- Children Vaccinated 2017 | OPV/Polio 1- Children Vaccinated 2018 | OPV/Polio 1- Children Vaccinated 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 466 | 435 | 476 | 551 | 409 | 449 |
| Ataase | 1800 | 1724 | 1934 | 1871 | 1825 | 1883 |
| New Edubiase | 1956 | 1416 | 1260 | 1565 | 1297 | 1200 |
| District | 4222 | 3575 | 3670 | 3987 | 3531 | 3532 |

| Organization unit name | PCV 1 - 2017 | PCV 1 - 2018 | PCV 1 - 2019 | Penta 1 - 2017 | Penta 1 - 2018 | Penta 1 -2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 551 | 409 | 449 | 551 | 409 | 449 |
| Ataase | 1871 | 1825 | 1883 | 1871 | 1825 | 1883 |
| New Edubiase | 1555 | 1297 | 1200 | 1555 | 1297 | 1200 |
| District | 3977 | 3531 | 3532 | 3977 | 3531 | 3532 |

| org | Rotavirus 1 -2017 | Rotavirus 1 - 2018 | Rotavirus 1 - 2019 | OPV/Polio 2 - 2017 | OPV/Polio 2 -2018 | OPV/Polio 2 - 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 551 | 409 | 449 | 442 | 393 | 459 |
| Ataase | 1871 | 1825 | 1883 | 1736 | 1710 | 1870 |
| New Edubiase | 1550 | 1297 | 1200 | 1654 | 1227 | 1207 |
| District | 3972 | 3531 | 3532 | 3832 | 3330 | 3536 |

| organisationunitname | PCV 2 - 2017 | PCV 2 -2018 | PCV 2 -2019 | Penta 2 - 2017 | Penta 2 - 2018 | Penta 2 -2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 363 | 442 | 393 | 363 | 442 | 459 |
| Ataase | 1738 | 1736 | 1710 | 1737 | 1736 | 1870 |
| New Edubiase | 1240 | 1654 | 1227 | 1240 | 1654 | 1207 |
| District | 3341 | 3832 | 3330 | 3340 | 3832 | 3536 |

| organisationunitname | Rotavirus 2 - 2017 | Rotavirus 2 - 2018 | Rotavirus 2 - 2019 | OPV/Polio 3 -2017 | OPV/Polio 3 -2018 | OPV/Polio 3 -2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 357 | 442 | 459 | 603 | 411 | 471 |
| Ataase | 1736 | 1736 | 1869 | 1934 | 1846 | 1913 |
| New Edubiase | 1240 | 1647 | 1207 | 1861 | 1290 | 1192 |
| District | 3333 | 3825 | 3535 | 4398 | 3547 | 3576 |

| organisationunitname | PCV 3 - 2017 | PCV 3 - 2018 | PCV 3 - 2019 | Penta 3 - 2017 | Penta 3 - 2018 | Penta 3 - 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 603 | 411 | 471 | 603 | 411 | 471 |
| Ataase | 1934 | 1846 | 1913 | 1934 | 1846 | 1913 |
| New Edubiase | 1861 | 1290 | 1194 | 1861 | 1290 | 1192 |
| District | 4398 | 3547 | 3578 | 4398 | 3547 | 3576 |

| organisationunitname | Measles Rubella 1 - 2017 | Measles Rubella 1 - 2018 | Measles Rubella 1 - 2019 | Yellow Fever - 2017 | Yellow Fever - 2018 | Yellow Fever - 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 488 | 438 | 436 | 488 | 438 | 436 |
| Ataase | 1769 | 1567 | 1554 | 1765 | 1567 | 1554 |
| New Edubiase | 1383 | 1072 | 947 | 1383 | 1072 | 947 |
| District | 3640 | 3077 | 2937 | 3636 | 3077 | 2937 |

| organisationunitname | Measles Rubella 2 - 2017 | Measles Rubella 2 - 2018 | Measles Rubella 2 - 2019 | Men A - 2017 | Men A - 2018 | Men A - 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 432 | 268 | 331 | 432 | 268 | 302 |
| Ataase | 1443 | 1326 | 1375 | 1443 | 1336 | 1245 |
| New Edubiase | 1193 | 897 | 729 | 1189 | 892 | 667 |
| District | 3068 | 2491 | 2435 | 3064 | 2496 | 2214 |

| organisationunitname | Vitamin A supplementation 6-11 months 2017 | Vitamin A supplementation 6-11 months 2018 | Vitamin A supplementation 6-11 months 2019 | Vitamin A supplementation >=12 months 2017 | Vitamin A supplementation >=12 months 2018 | Vitamin A supplementation >=12 months 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 719 | 390 | 405 | 1974 | 1356 | 1697 |
| Ataase | 1609 | 1826 | 2202 | 4879 | 5583 | 6746 |
| New Edubiase | 1694 | 1103 | 1081 | 8785 | 4266 | 2454 |
| District | 4022 | 3319 | 3688 | 15638 | 11205 | 10897 |

| organisationunitname | LLIN given to children 2017 | LLIN given to children 2018 | LLIN given to children 2019 | Total CWC Registrants (0-59 months )weighed 2017 | Total CWC Registrants (0-59 months )weighed 2018 | Total CWC Registrants (0-59 months )weighed 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 372 | 268 | 323 | 789 | 730 | 738 |
| Ataase | 1115 | 1211 | 1309 | 2366 | 2820 | 1973 |
| New Edubiase | 625 | 832 | 690 | 3238 | 3124 | 1896 |
| District | 2112 | 2311 | 2322 | 6393 | 6674 | 4607 |

RCH

| organisationunitname | ANC registrants 2017 | ANC registrants 2018 | ANC registrants 2019 | Mothers making 4th ANC visit 2017 | Mothers making 4th ANC visit 2018 | Mothers making 4th ANC visit 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 171 | 221 | 230 | 96 | 140 | 281 |
| Ataase | 926 | 824 | 865 | 600 | 563 | 693 |
| New Edubiase | 1173 | 1207 | 1151 | 1006 | 861 | 856 |
| District | 2270 | 2252 | 2246 | 1702 | 1564 | 1830 |

| organisationunitname | Td 2+ vaccinations at ANC 2017 | Td 2+ vaccinations at ANC 2018 | Td 2+ vaccinations at ANC 2019 | Haemoglobin checked at ANC registration 2017 | Haemoglobin checked at ANC registration 2018 | Haemoglobin checked at ANC registration 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 107 | 212 | 370 | 105 | 190 | 230 |
| Ataase | 1533 | 1260 | 750 | 893 | 820 | 843 |
| New Edubiase | 699 | 674 | 847 | 1173 | 1207 | 1151 |
| District | 2339 | 2146 | 1967 | 2171 | 2217 | 2224 |

| organisationunitname | Haemoglobin < 11gm/dl at ANC registration 2017 | Haemoglobin < 11gm/dl at ANC registration 2018 | Haemoglobin < 11gm/dl at ANC registration 2019 | Haemoglobin checked at 36 weeks of pregnancy 2017 |  |  | Haemoglobin checked at 36 weeks of pregnancy 2018 |  | Haemoglobin checked at 36 weeks of pregnancy 2019 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 71 | 141 | 116 | 45 |  |  | 94 |  | 129 |  |
| Ataase | 344 | 315 | 211 | 474 |  |  | 354 |  | 243 |  |
| New Edubiase | 489 | 852 | 502 | 709 |  |  | 839 |  | 663 |  |
| District | 904 | 1308 | 829 | 1228 |  |  | 1287 |  | 1035 |  |
| organisationunitname | Haemoglobin < 11gm/dl at 36 weeks of pregnancy 2017 | Haemoglobin < 11gm/dl at 36 weeks of pregnancy 2018 | Haemoglobin < 11gm/dl at 36 weeks of pregnancy 2019 |  | Antenatal mother at registration - 10-14 2017 | Antenatal mother at registration - 10-14 2018 |  | Antenatal mother at registration - 10-14 2019 |  |
| Akutreso | 23 | 71 | 99 |  | 1 | 0 |  |  |  |
| Ataase | 173 | 153 | 120 |  | 7 | 25 |  | 6 |  |
| New Edubiase | 330 | 462 | 87 |  | 3 | 9 |  | 8 |  |
| District | 526 | 686 | 306 |  | 11 | 34 |  | 14 |  |

| organisationunitname | Antenatal mother at registration - 15 - 19 2017 | Antenatal mother at registration - 15 - 19 2018 | Antenatal mother at registration - 15 - 19 2018 | Mothers below 150 cm (5ft) 2017 | Mothers below 150 cm (5ft) 2018 | Mothers below 150 cm (5ft) 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 38 | 39 | 44 | 5 | 24 | 23 |
| Ataase | 174 | 172 | 168 | 23 | 0 | 16 |
| New Edubiase | 178 | 216 | 178 | 53 | 65 | 61 |
| District | 390 | 427 | 390 | 81 | 89 | 100 |

| organisationunitname | Parity: ≥ 5 2017 | Parity: ≥ 5 2018 | Parity: ≥ 5 2019 | Mothers registered in 3rd trimester 2017 | Mothers registered in 3rd trimester 2018 | Mothers registered in 3rd trimester 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 15 | 51 | 52 | 31 | 46 | 52 |
| Ataase | 137 | 93 | 92 | 143 | 152 | 113 |
| New Edubiase | 134 | 113 | 83 | 107 | 103 | 53 |
| District | 286 | 257 | 227 | 281 | 301 | 218 |

| organisationunitname | IPT 1 2017 | IPT 1 2018 | IPT 1 2019 | IPT 2 2017 | IPT 2 2018 | IPT 2 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 129 | 196 | 255 | 101 | 131 | 174 |
| Ataase | 465 | 533 | 507 | 391 | 387 | 391 |
| New Edubiase | 722 | 651 | 651 | 540 | 483 | 518 |
| District | 1316 | 1380 | 1413 | 1032 | 1001 | 1083 |

| organisationunitname | IPT 4 2017 | IPT 4 2018 | IPT 4 2019 | IPT 3 2017 | IPT 3 2018 | IPT 3 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 39 | 45 | 74 | 65 | 73 | 134 |
| Ataase | 142 | 122 | 103 | 239 | 238 | 237 |
| New Edubiase | 188 | 143 | 225 | 351 | 270 | 379 |
| District | 369 | 310 | 402 | 655 | 581 | 750 |

| organisationunitname | IPT 5 2017 | IPT 5 2018 | IPT 5 2019 | Total Deliveries 2017 | Total Deliveries 2018 | Total Deliveries 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 8 | 13 | 42 | 43 | 91 | 164 |
| Ataase | 91 | 79 | 44 | 423 | 395 | 424 |
| New Edubiase | 107 | 78 | 77 | 836 | 771 | 916 |
| District | 206 | 170 | 163 | 1302 | 1257 | 1504 |

| organisationunitname | Caesarean section deliveries 2017 | Caesarean section deliveries 2018 | Caesarean section deliveries 2019 | Live births (Total) 2017 | Live births (Total) 2018 | Live births (Total) 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso |  |  |  | 43 | 89 | 164 |
| Ataase |  |  |  | 387 | 399 | 431 |
| New Edubiase | 170 | 121 | 181 | 825 | 770 | 920 |
| District | 170 | 121 | 181 | 1255 | 1258 | 1515 |

| organisationunitname | Total Still Birth 2017 | Total Still Birth 2018 | Total Still Birth 2019 | Total maternal deaths 2017 | Total maternal deaths 2018 | Total maternal deaths 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 0 | 0 |  | 0 | 0 | 0 |
| Ataase | 0 | 0 | 1 | 0 | 0 | 0 |
| New Edubiase | 33 | 12 | 18 | 1 | 2 | 1 |
| District | 33 | 12 | 19 | 1 | 2 | 1 |

| organisationunitname | Total number of deliveries with birth weight < 2.5kg 2017 | Total number of deliveries with birth weight < 2.5kg 2017 | Total number of deliveries with birth weight < 2.5kg 2019 | Total PNC registrants 2017 | Total PNC registrants 2018 | Total PNC registrants 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 5 | 4 |  | 84 | 121 | 166 |
| Ataase | 45 | 26 | 20 | 500 | 539 | 542 |
| New Edubiase | 157 | 148 | 144 | 1112 | 850 | 968 |
| District | 207 | 178 | 164 | 1696 | 1510 | 1676 |

| organisationunitname | 1st PNC on day 1 or 2 2017 | 1st PNC on day 1 or 2 2018 | 1st PNC on day 1 or 2 2019 | 1st PNC on day 3-7 2017 | 1st PNC on day 3-7 2018 | 1st PNC on day 3-7 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 48 | 92 | 159 | 19 | 15 | 5 |
| Ataase | 332 | 395 | 418 | 85 | 105 | 83 |
| New Edubiase | 920 | 781 | 921 | 160 | 18 | 11 |
| District | 1300 | 1268 | 1498 | 264 | 138 | 99 |

| organisationunitname | 1st PNC from day 8 and above 2017 | 1st PNC from day 8 and above 2018 | 1st PNC from day 8 and above 2019 | CAC 2017 | CAC 2018 | CAC 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 17 | 14 | 2 | 0 | 0 |  |
| Ataase | 83 | 39 | 41 | 168 | 94 | 78 |
| New Edubiase | 32 | 51 | 36 | 125 | 133 | 142 |
| District | 132 | 104 | 79 | 293 | 227 | 220 |

| organisationunitname | Clients tested for HIV(HTC) 2017 | Clients tested for HIV(HTC) 2018 | Clients tested for HIV(HTC) 2019 | Clients tested HIV positive(HTC) 2017 | Clients tested HIV positive(HTC) 2018 | Clients tested HIV positive(HTC) 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 8 | 29 | 2 | 2 | 3 | 1 |
| Ataase | 55 | 15 |  | 9 |  |  |
| New Edubiase | 373 | 707 | 2682 | 42 | 45 | 90 |
| District | 436 | 751 | 2684 | 53 | 48 | 91 |

| organisationunitname | Pregnant women tested for HIV 2017 | Pregnant women tested for HIV 2018 | Pregnant women tested for HIV 2019 | Pregnant women tested HIV positive (PMTCT) at registration 2017 | Pregnant women tested HIV positive (PMTCT) at registration 2018 | Pregnant women tested HIV positive( PMTCT) at registration 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 127 | 206 | 230 | 0 | 1 |  |
| Ataase | 892 | 820 | 824 | 6 | 1 |  |
| New Edubiase | 1096 | 1207 | 1151 | 15 | 9 |  |
| District | 2115 | 2233 | 2205 | 21 | 11 |  |

| organisationunitname | Total couple year protection 2017 | Total couple year protection 2018 | Total couple year protection 2019 | Total Family Planning Continuing Acceptors 2017 | Total Family Planning Continuing Acceptors 2018 | Total Family Planning Continuing Acceptors 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 598.9 | 535.1 | 1126.3 | 347 | 594 | 1219 |
| Ataase | 3536.3 | 1717.3 | 2750 | 2128 | 2368 | 2655 |
| New Edubiase | 1241.6 | 1508.7 | 1915.8 | 1265 | 2141 | 1137 |
| District | 5376.8 | 3761.1 | 5792.1 | 3740 | 5103 | 5011 |

| organisationunitname | Total Family Planning New Acceptors 2017 | Total Family Planning New Acceptors 2018 | Total Family Planning New Acceptors 2019 | Total family planning registrants 2017 | Total family planning registrants 2018 | Total family planning registrants 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 273 | 131 | 408 | 366 | 143 | 407 |
| Ataase | 899 | 747 | 1009 | 780 | 620 | 994 |
| New Edubiase | 682 | 658 | 824 | 693 | 610 | 734 |
| District | 1854 | 1536 | 2241 | 1839 | 1373 | 2135 |

| organisationunitname | Total number of malaria cases suspected 2017 | Total number of malaria cases suspected 2018 | Total number of malaria cases suspected 2019 | Total number of malaria cases suspected tested 2017 | Total number of malaria cases suspected tested 2018 | Total number of malaria cases suspected tested 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 1291 | 1914 | 3370 | 1236 | 1877 | 3342 |
| Ataase | 8937 | 11618 | 8956 | 8850 | 11611 | 9420 |
| New Edubiase | 8726 | 14267 | 12747 | 8722 | 14186 | 12747 |
| District | 24911 | 38065 | 25073 | 23912 | 37732 | 25509 |

| organisationunitname | Total number of malaria cases tested positive 2017 | Total number of malaria cases tested positive 2018 | Total number of malaria cases tested positive 2019 | Uncomplicated Malaria not tested but treated as malaria 2017 | Uncomplicated Malaria not tested but treated as malaria 2018 | Uncomplicated Malaria not tested but treated as malaria 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 779 | 1158 | 2177 | 58 | 33 | 0 |
| Ataase | 6497 | 8121 | 7199 | 151 |  | 0 |
| New Edubiase | 2374 | 6598 | 6934 | 5 | 51 | 0 |
| District | 9650 | 15877 | 16310 | 214 | 84 | 0 |

| organisationunitname | OPD Attendance Insured 2017 | OPD Attendance Insured 2018 | OPD Attendance Insured 2019 | Total OPD attendance 2017 | Total OPD attendance 2018 | Total OPD attendance 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Akutreso | 1298 | 1533 | 2834 | 1627 | 2012 | 3666 |
| Ataase | 8923 | 9810 | 8128 | 10658 | 12064 | 10033 |
| New Edubiase | 33860 | 33315 | 33800 | 38475 | 39282 | 40188 |
| District | 44081 | 44658 | 44762 | 50760 | 53358 | 53887 |

HUMAN RESOURCE INFORMATION

| NO | STAFF CATEGORY | 2018 | 2019 |
| --- | --- | --- | --- |
| 1 | Accountant | 2 | 6 |
| 2 | Administrative Manager | 1 | 2 |
| 2 | Health Service Administrator | 1 | 1 |
| 3 | Executive Officer | 1 | 1 |
| 4 | Medical Superintendent | 1 | 1 |
| 5 | Medical Officer | 1 | 2 |
| 6 | Physician Assistant (Dental) | 1 | 1 |
| 7 | Physician Assistant | 3 | 3 |
| 8 | Physician Assistant (Medical) | 3 | 3 |
| 9 | Medical Assistant | 2 | 2 |
| 10 | Physician Assistant Anaes. | 2 | 2 |
| 11 | Internal Auditor | 1 | 1 |
| 12 | Tech. Officer (Health Information) | 2 | 2 |
| 13 | Tech. Officer (Biostat) | 2 | 2 |
| 15 | Mortuary Attendant | 1 | 1 |
| 16 | Biomedical Scient. | 1 | 1 |
| 17 | Technical officers (Disease Control) | 2 | 2 |
| 18 | Field Technician | 3 | 3 |
| 19 | Technical Officer (Med. Lab) | 2 | 2 |
| 20 | Physio And Orthotics Assist | 2 | 2 |
| 21 | Pharmacist | 2 | 5 |
| 22 | Pharmacy Technician | 3 | 3 |
| 23 | Dispensing Assistant | 4 | 4 |
| 24 | Supply Officer | 1 | 1 |
| 25 | Watchman | 2 | 2 |
| 26 | Orderly | 11 | 11 |
| 27 | Deputy Director of Nursing | 2 | 2 |
| 28 | Senior Nursing Officer | 2 | 2 |
| 29 | Nursing Officer | 5 | 5 |
| 30 | Nutrition officer | 1 | 1 |
| 31 | Finance Officer | 1 | 1 |
| 32 | Secretary | 1 | 1 |
| 33 | Registered General Nurse | 33 | 33 |
| 34 | Registered General Nurse (Mental Health) | 3 | 4 |
| 35 | Technical Officer - Community Mental Health | 2 | 2 |
| 36 | Midwifery Officer | 3 | 3 |
| 37 | Senior Staff Midwife | 14 | 14 |
| 38 | Staff Midwife | 11 | 11 |
| 39 | Enrolled Nurse | 58 | 50 |
| 40 | Community Health Nurse | 53 | 53 |
| 41 | District Director | 1 | 1 |
| 42 | Driver | 1 | 1 |
| 41 | Health Assistant | 14 | 11 |
| 42 | Total established Staff | 262 | 249 |
| 39 | Casual Staff | 45 | 45 |
| 40 | National Service | 24 | 24 |
| 41 | NABCO Staff | 22 | 22 |
| 42 | Rotation Nurses | 33 | 33 |
| 43 | Total Non-Established Staff | 124 | 124 |

Table 2.3: Growth monitoring trend (0-59 months), 2017 -2019

| INDICATOR | 2017 | 2018 | 2019 |
| --- | --- | --- | --- |
| Registrants | 8926 | 8308 | 4607 |
| Attendance | 77471 | 78182 | 56127 |
| Normal Weight (Attend) | 73175 | 75355 | 53875 |
| Moderate Underweight (Attend) | 3238 | 2797 | 1233 |
| Severe Underweight (Attend) | 65 | 64 | 30 |

Table 2.4: Breastfeed programme

| INDICATOR | 2017 | 2018 | 2019 |
| --- | --- | --- | --- |
| Expected Deliveries | 5561 | 5319 | 3948 |
| No. of Deliveries (Mother/babies) | 1612/1643 | 1618/1636 | 1504/1534 |
| Babies put to breast within 1hr | 1579 | 1636 | 1510 |
| Exclusive Breastfeeding | 1552 | 1576 | 1534 |

Table 2.5: Trend of Diet Related Diseases 2017-2019

| TYPE OF DISEASE | 2017 |  |  | 2018 |  |  | 2019 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Total | Male | Female | Total | Male | Female | Total |
| Hypertension | 358 | 767 | 1125 | 199 | 288 | 487 | 126 | 253 | 379 |
| Diabetes | 42 | 87 | 129 | 41 | 63 | 104 | 47 | 89 | 136 |

Table 2.6: Anaemia

| Indicator | Total Checked |  |  | <11g/dl |  |  |  | <7g/dl |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 |  | 2017 | 2018 | 2019 |  | 2017 | 2018 | 2019 |
| At Registration | 2802 | 2812 | 2224 |  | 1058 | 1384 | 829 |  | 7 | 26 | 64 |
| At Term | 1605 | 1649 | 1035 |  | 628 | 745 | 306 |  | 2 | 1 | 1 |

Table 2.7: Trend of Vitamin A Supplementation, 2017-2019

| Indicator | Target (6-11 months) | Performance (6-11 months) | Target (12-59 months) | Performance (12 – 59 months) | Target (6-59 months) | Performance (6-59 months) |
| --- | --- | --- | --- | --- | --- | --- |
| 2017 | 2856 | 6048 (212%) | 22846 | 19926 (87.2%) | 25702 | 25974 (101%) |
| 2018 | 2728 | 4675 (171%) | 21822 | 14419 (66%) | 24550 | 19094 (78%) |
| 2019 | 1974 | 3688(186.8%) | 14,311 | 10,897(76.0%) | 16,285 | 14,585(89.6%) |
| 2020 |  |  |  |  |  |  |

| Subdistrict | Posted in | Posted out | Vacated post |
| --- | --- | --- | --- |
| Ataase | 5(10.6%) | 3(23%) | 0 |
| Akutreso | 4(8.5%) | 0 | 1 |
| New Edubiase | 38 (80.9%0 | 10(77%) | 0 |
| Total | 47(100%) | 13 (100%) | 1 |

Staff strength

As at December, 2019 the total staff were three hundred and sixty (360) of which 68.9% were established post with 31.1% being non established post (casuals). Majority (74%) of the total staff work at the district hospital with few (5.3%) at Akutreso subdistrict.

Table 2.11: The staff strength by sub-districts, 2019

| Subdistrict | Established | Non-established | Total |
| --- | --- | --- | --- |
| Ataase | 45 | 4 | 49(15.3%) |
| Akutreso | 16 | 1 | 17(5.3%) |
| Hospital | 174 | 63 | 237(74.0%) |
| Directorate | 13 | 4 | 17(5.3%) |
| Total | 248 | 72 | 320(100%) |